## Project
PROJECTSWP – RESTAURANT MANAGEMENT SYSTEM – FINAL PROJECT TRACKING
Class SE20A11 ¦ Group 01 ¦ Version 3.0 ¦ 90 auditable UI/non-UI functions ¦ Repository-aligned baseline for final defense.
Audit rule: Done/Updated requires implementation plus final-tag build/test, secured API, real UI integration, database proof, matching RDS/SDS, and registered evidence. Experimental work is never counted as complete.
No. | Work ID | Screen / Function | Feature | Function Type | Actor | Detailed Description | Business Rules / Validation | Acceptance Criteria | Planned Iteration | Actual Iteration | Updated Iteration | In Charge | Priority | Complexity | Target LOC Band | Status | SRS Ref | SDS Ref | Trace / Evidence ID | Risk / Update Notes | Audit Evidence Status
1 | AUTH-01 | Login Screen & Client Validation | Authentication & Security | UI Screen | Guest, All Users | Presents email/password fields, validates required format, shows field-level errors, and redirects authenticated users to the correct role workspace. | Email is required and normalized; password is never exposed in logs; repeated submissions are prevented while a request is processing. | Valid input submits once; invalid input remains on screen with clear messages; successful login redirects by role without exposing credentials. | Iter1 | Iter1 | none | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Done | II.1.1 | II.1.1 | EV-AUTH-01 / TC-AUTH-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
2 | AUTH-02 | Credential Authentication API | Authentication & Security | Backend API | Guest | Authenticates a submitted email and password against an active user account and returns a standardized success or failure response. | Inactive/locked accounts cannot log in; comparisons use encoded passwords; authentication failures must not reveal whether an email exists. | Correct credentials succeed; wrong password, unknown email, and inactive account return safe errors; API contract is covered by tests. | Iter1 | Iter1 | none | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Done | II.1.2 | II.1.2 | EV-AUTH-02 / TC-AUTH-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
3 | AUTH-03 | Password Hashing & Credential Verification | Authentication & Security | Security Service | Guest, All Users | Encodes passwords before persistence and verifies credentials through the configured password encoder. | Plaintext passwords must never be stored or returned; encoding configuration is consistent across registration, reset, and login. | Database contains only encoded passwords; registration/reset/login use the same encoder; negative password tests pass. | Iter1 | Iter1 | none | Phạm Văn Quyết (DE190425) | Critical | Medium | 120 | Done | II.1.3 | II.1.3 | EV-AUTH-03 / TC-AUTH-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
4 | AUTH-04 | JWT Access Token Generation | Authentication & Security | Security Service | Authenticated Users | Creates a signed access token containing the user identity, role claims, issue time, and expiration after successful authentication. | Signing key is externalized; token lifetime is configurable; only required non-sensitive claims are included. | A valid login returns a signed token; signature and expiration can be verified; tampered tokens are rejected. | Iter1 | Iter1 | Iter4 | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Done | II.1.4 | II.1.4 | EV-AUTH-04 / TC-AUTH-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
5 | AUTH-05 | JWT Refresh Token Persistence | Authentication & Security | Backend Service / DB | Authenticated Users | Stores refresh-token hashes and lifecycle metadata so an expired access token can be renewed without re-entering credentials. | Refresh tokens are one-way hashed, revocable, unique, time-limited, and bound to a user account. | Valid refresh creates a new access token; expired/revoked/reused tokens fail; raw refresh tokens are not persisted. | Iter1 | Iter1 | none | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Done | II.1.5 | II.1.5 | EV-AUTH-05 / TC-AUTH-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
6 | AUTH-06 | JWT Authentication Filter | Authentication & Security | Security Filter | Authenticated Users | Reads the bearer token on every protected request, validates it, and populates the authenticated security context. | Public endpoints bypass authentication; malformed headers and invalid tokens do not create a security context. | Protected requests with valid tokens reach controllers; missing/invalid/expired tokens return 401; public routes remain accessible. | Iter1 | Iter1 | Iter4 | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Done | II.1.6 | II.1.6 | EV-AUTH-06 / TC-AUTH-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
7 | AUTH-07 | Token Expiry & Invalid Token Handling | Authentication & Security | Exception Handling | Authenticated Users | Returns consistent error responses for expired, malformed, unsupported, or incorrectly signed tokens. | Security errors use the common API error format; sensitive token details are not logged or returned. | Each invalid-token scenario returns the expected HTTP status and message; frontend can distinguish expiry from authorization failure. | Iter1 | Iter1 | Iter4 | Phạm Văn Quyết (DE190425) | Critical | Medium | 120 | Done | II.1.7 | II.1.7 | EV-AUTH-07 / TC-AUTH-07 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
8 | AUTH-08 | Endpoint Role Authorization Matrix | Authentication & Security | Authorization Policy | Admin, Staff, Kitchen Staff, Customer | Defines explicit access rules for all protected API groups and matches them with frontend role navigation. | Admin-only write APIs reject non-admins; users may access only owned resources; deny-by-default applies to unmatched protected routes. | Authorization tests prove 401 for unauthenticated and 403 for wrong-role requests across representative endpoints. | Iter1 | Iter1 | Iter4 | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Done | II.1.8 | II.1.8 | EV-AUTH-08 / TC-AUTH-08 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
9 | AUTH-09 | Standard 401/403 Security Responses | Authentication & Security | Exception Handling | All Users | Converts authentication and authorization failures into predictable JSON responses consumed by the frontend. | 401 is used for missing/invalid authentication; 403 is used for authenticated users without permission. | Frontend receives stable error codes/messages; no HTML error page is returned by secured APIs; tests cover both statuses. | Iter1 | Iter1 | Iter4 | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Done | II.1.9 | II.1.9 | EV-AUTH-09 / TC-AUTH-09 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
10 | AUTH-10 | Logout & Token Revocation | Authentication & Security | Backend API | Authenticated Users | Ends an authenticated session by revoking the current refresh token and clearing client authentication state. | Revoked tokens cannot be reused; logout is idempotent; client removes access and refresh credentials. | After logout, refresh fails and protected requests require a new login; repeated logout requests do not create errors. | Iter1 | Iter1 | none | Phạm Văn Quyết (DE190425) | High | Medium | 120 | Done | II.1.10 | II.1.10 | EV-AUTH-10 / TC-AUTH-10 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
11 | AUTH-11 | Registration Screen & Validation | Authentication & Security | UI Screen | Guest | Collects customer account information, validates required fields and password confirmation, and displays API validation errors. | Email format and required profile fields are validated; password confirmation must match; submit is disabled while processing. | Valid data creates an account; invalid fields show messages; duplicate email feedback is shown without page crash. | Iter1 | Iter1 | none | Phan Nguyễn (DE191019) | High | Medium | 120 | Done | II.1.11 | II.1.11 | EV-AUTH-11 / TC-AUTH-11 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
12 | AUTH-12 | Registration API & Duplicate Email Check | Authentication & Security | Backend API | Guest | Creates a customer account with the default role after validating input and uniqueness constraints. | Email is unique case-insensitively; password is encoded; clients cannot self-assign privileged roles. | New account is persisted with customer role; duplicate email and invalid input are rejected; tests verify role protection. | Iter1 | Iter1 | none | Phan Nguyễn (DE191019) | High | Complex | 240 | Done | II.1.12 | II.1.12 | EV-AUTH-12 / TC-AUTH-12 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
13 | AUTH-13 | Forgot Password Request | Authentication & Security | UI / Backend API | Guest | Allows a user to request a reset token or code without revealing whether the submitted email is registered. | Response is generic; reset tokens expire and are single-purpose; request rate should be limited. | Request always returns a safe response; valid accounts receive a usable reset token/code; repeated abuse is handled. | Iter1 | Iter1 | none | Nguyễn Đức Thương (DE190096) | Medium | Complex | 240 | Done | II.1.13 | II.1.13 | EV-AUTH-13 / TC-AUTH-13 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
14 | AUTH-14 | Reset Password Token Validation | Authentication & Security | Backend API | Guest | Validates the reset token/code, saves a new encoded password, and invalidates the token after successful use. | Expired, invalid, or reused tokens are rejected; new password rules and confirmation are enforced. | Valid token updates the password once; old password stops working; expired/reused token tests pass. | Iter1 | Iter1 | none | Phạm Văn Quyết (DE190425) | High | Complex | 240 | Done | II.1.14 | II.1.14 | EV-AUTH-14 / TC-AUTH-14 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
15 | USER-01 | View Own Profile | User Management | UI / Backend API | Customer, Staff, Kitchen Staff, Admin | Displays the authenticated user's profile and contact information using the current security identity. | A user can only read their own profile through this function; sensitive fields and password hashes are excluded. | Profile loads after login, contains only permitted fields, and rejects attempts to read another user's data. | Iter1 | Iter1 | none | Phan Nguyễn (DE191019) | Medium | Complex | 240 | Done | II.2.1 | II.2.1 | EV-USER-01 / TC-USER-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
16 | USER-02 | Update Own Profile | User Management | UI / Backend API | Customer, Staff, Kitchen Staff, Admin | Allows permitted personal/contact fields and avatar data to be updated while preserving role, status, and credentials. | Protected fields cannot be changed; duplicate contact information and invalid formats are rejected. | Permitted changes persist after refresh; protected-field tampering is ignored/rejected; validation messages are clear. | Iter1 | Iter1 | Iter3 | Nguyễn Đức Thương (DE190096) | High | Complex | 240 | Updated | II.2.2 | II.2.2 | EV-USER-02 / TC-USER-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
17 | USER-03 | Admin User List & Search | User Management | Admin Screen / API | Admin | Provides paginated account listing with search and filters by role and account status. | Only administrators can access; returned data excludes passwords and security secrets; pagination is stable. | Admin can load, search, filter, and open account details; non-admin requests return 403; empty results are handled. | Iter1 | Iter1 | Iter4 | Nguyễn Đức Thương (DE190096) | Critical | Complex | 240 | Done | II.2.3 | II.2.3 | EV-USER-03 / TC-USER-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
18 | USER-04 | Admin Change Role / Lock Account | User Management | Admin API | Admin | Allows safe role updates and account activation/locking with protection for critical accounts and active sessions. | Admin cannot remove the last active administrator or lock the currently required system account; changes are audited. | Allowed changes persist and affect authorization; unsafe changes are blocked; account lock prevents login immediately. | Iter1 | Iter1 | none | Phan Nguyễn (DE191019) | Critical | Complex | 240 | Done | II.2.4 | II.2.4 | EV-USER-04 / TC-USER-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
19 | MENU-01 | Category List | Menu Management | Admin Screen / API | Admin | Lists categories with status, search, and item usage information for administration. | Only active categories appear in customer menu; admin list may include inactive categories. | Admin can search and filter categories; list reflects database state and handles no-data cases. | Iter1 | Iter1 | none | Phan Nguyễn (DE191019) | Medium | Medium | 120 | Done | II.3.1 | II.3.1 | EV-MENU-01 / TC-MENU-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
20 | MENU-02 | Create / Update Category | Menu Management | Admin Screen / API | Admin | Creates and edits menu categories with normalized names and optional descriptions. | Category names are required and unique case-insensitively; invalid input does not alter data. | Create/update persists valid data; duplicates and blank names are rejected with clear feedback. | Iter1 | Iter1 | none | Phan Nguyễn (DE191019) | High | Medium | 120 | Done | II.3.2 | II.3.2 | EV-MENU-02 / TC-MENU-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
21 | MENU-03 | Deactivate Category & Referential Rule | Menu Management | Admin API | Admin | Deactivates a category while preserving historical references and preventing unsafe deletion when foods still depend on it. | Referenced categories are not hard-deleted; deactivation hides them from new customer selections. | Deactivation is safe and reversible; existing historical food/order data remains valid. | Iter1 | Iter1 | none | Phan Nguyễn (DE191019) | High | Complex | 240 | Done | II.3.3 | II.3.3 | EV-MENU-03 / TC-MENU-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
22 | MENU-04 | Admin Food List / Search / Filter | Menu Management | Admin Screen / API | Admin | Lists foods with category, price, availability, status, and keyword/category filters. | Pagination and filters must use server data; inactive items remain visible to admin only. | Search/filter results are correct; list refreshes after changes; no-data and API-error states are shown. | Iter1 | Iter1 | Iter4 | Phan Nguyễn (DE191019) | High | Medium | 120 | Updated | II.3.4 | II.3.4 | EV-MENU-04 / TC-MENU-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
23 | MENU-05 | Create / Update Food Item | Menu Management | Admin Screen / API | Admin | Creates and edits food name, category, price, description, image reference, status, and availability. | Price must be positive; category must exist and be active for new assignments; duplicate business rules are enforced. | Valid foods persist and appear in the proper menu; invalid price/category/data are rejected; updates preserve order history snapshots. | Iter1 | Iter1 | Iter4 | Phan Nguyễn (DE191019) | High | Complex | 240 | Updated | II.3.5 | II.3.5 | EV-MENU-05 / TC-MENU-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
24 | MENU-06 | Food Image & Availability Management | Menu Management | UI / Backend API | Admin | Updates food image metadata and operational availability separately from active master-data status. | Unavailable food cannot be newly added to cart/order; existing historical orders retain the original item reference. | Image/availability changes persist; customer menu updates; unavailable item ordering is blocked server-side. | Iter1 | Iter1 | Iter4 | Nguyễn Đức Thương (DE190096) | High | Complex | 240 | Updated | II.3.6 | II.3.6 | EV-MENU-06 / TC-MENU-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
25 | MENU-07 | Customer Menu Browse / Detail / Filter | Menu Management | Customer Screen | Guest, Customer | Displays active available foods grouped by category with details, keyword search, and category filtering. | Only active/available foods and active categories are exposed; prices come from server data. | Customer can browse and filter live menu data; unavailable items are hidden/disabled; cart entry points work. | Iter1 | Iter1 | none | Phan Nguyễn (DE191019) | High | Medium | 120 | Done | II.3.7 | II.3.7 | EV-MENU-07 / TC-MENU-07 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
26 | TABLE-01 | View Table List & Availability | Table Management | UI / Backend API | Customer, Staff, Admin | Displays restaurant tables with table number, capacity, status, and availability appropriate to the current role. | Customers see reservable information; staff/admin may see operational status; inactive tables are excluded from new reservations. | Role-appropriate table data loads correctly; statuses match database state; no-data and error states are handled. | Iter2 | Iter2 | none | Nguyễn Đức Thương (DE190096) | High | Complex | 240 | Done | II.4.1 | II.4.1 | EV-TABLE-01 / TC-TABLE-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
27 | TABLE-02 | Admin Create / Update Table | Table Management | Admin Screen / API | Admin | Creates and edits restaurant table master data including number, capacity, status, and active flag. | Table number is unique; capacity is positive and within configured limits; referenced tables are not unsafely deleted. | Valid changes persist; duplicates and invalid capacity are rejected; updates appear in reservation/staff screens. | Iter2 | Iter2 | Iter3 | Phạm Văn Quyết (DE190425) | High | Complex | 240 | Updated | II.4.2 | II.4.2 | EV-TABLE-02 / TC-TABLE-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
28 | TABLE-03 | Table Capacity Validation | Table Management | Business Service | Admin, Staff, Customer | Validates table capacity during table maintenance, reservation matching, and staff assignment. | Capacity must be a positive integer; party size cannot exceed selected table capacity. | Invalid capacity and oversized party selections are rejected consistently in UI and API tests. | Iter2 | Iter2 | none | Phạm Văn Quyết (DE190425) | High | Medium | 120 | Done | II.4.3 | II.4.3 | EV-TABLE-03 / TC-TABLE-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
29 | TABLE-04 | Table Number Uniqueness | Table Management | Database / Service Validation | Admin | Prevents duplicate table numbers through service validation and a database uniqueness constraint. | Comparison is normalized; concurrent creation cannot produce duplicates. | Duplicate requests return a conflict/validation error and only one table record exists after concurrent tests. | Iter2 | Iter2 | none | Phan Nguyễn (DE191019) | High | Medium | 120 | Done | II.4.4 | II.4.4 | EV-TABLE-04 / TC-TABLE-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
30 | TABLE-05 | Table Operational Status Update | Table Management | Staff / Admin API | Staff, Admin | Updates operational table state such as available, reserved, occupied, or unavailable with controlled transitions. | Transitions must respect active reservations/orders and cannot silently overwrite conflicting state. | Allowed transitions succeed; invalid transitions return business errors; reservation/order flows remain synchronized. | Iter2 | Iter2 | Iter3 | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Updated | II.4.5 | II.4.5 | EV-TABLE-05 / TC-TABLE-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
31 | TABLE-06 | Table Search & Filter | Table Management | UI / Backend API | Staff, Admin | Supports search and filtering by table number, capacity, active flag, and operational status. | Filters are server-compatible and stable with pagination; role restrictions remain applied. | Combined filters return correct records and reset correctly; empty results display cleanly. | Iter2 | Iter2 | none | Trần Thanh Gia Huy (DE180571) | Medium | Complex | 240 | Done | II.4.6 | II.4.6 | EV-TABLE-06 / TC-TABLE-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
32 | RES-01 | Create Reservation Form | Reservation Management | Customer Screen | Customer | Collects reservation date, time, party size, selected table, and optional notes with clear validation. | Past times are not allowed; party size is positive; selected table must remain available at submission. | Valid form submits once; invalid date/time/party/table shows clear messages; success displays reservation details. | Iter2 | Iter2 | none | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Done | II.5.1 | II.5.1 | EV-RES-01 / TC-RES-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
33 | RES-02 | Search Available Tables | Reservation Management | Backend API | Customer, Staff | Returns tables available for a requested time range and party size. | Inactive/unavailable/undersized tables and overlapping active reservations are excluded. | Results match direct database checks; unavailable tables are never returned; boundary times are tested. | Iter2 | Iter2 | Iter4 | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Updated | II.5.2 | II.5.2 | EV-RES-02 / TC-RES-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
34 | RES-03 | Reservation Capacity Matching | Reservation Management | Business Service | Customer, Staff | Matches party size with eligible table capacity and validates a manually selected table before saving. | Selected table capacity must be greater than or equal to party size; capacity cannot be bypassed from the client. | Oversized reservations are rejected server-side; valid matching returns appropriate tables. | Iter2 | Iter2 | none | Phạm Văn Quyết (DE190425) | High | Medium | 120 | Done | II.5.3 | II.5.3 | EV-RES-03 / TC-RES-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
35 | RES-04 | Reservation Overlap & Concurrency Prevention | Reservation Management | Business Service / DB Lock | Customer, Staff | Prevents two active reservations from occupying the same table during overlapping time ranges, including concurrent submissions. | Overlap considers configured duration/statuses; final availability is checked inside the transaction using locking. | Sequential and concurrent overlap tests allow only one conflicting reservation; non-overlapping reservations succeed. | Iter2 | Iter2 | Iter4 | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Updated | II.5.4 | II.5.4 | EV-RES-04 / TC-RES-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
36 | RES-05 | Reservation Persistence Transaction | Reservation Management | Backend Service / DB | Customer, Staff | Creates the reservation atomically after revalidating user, table, time, capacity, and overlap rules. | Failed validation rolls back fully; createdBy/customer identity comes from the authenticated context. | Successful reservation has complete data; failures create no partial record; ownership is correct. | Iter2 | Iter2 | none | Phạm Văn Quyết (DE190425) | High | Complex | 240 | Done | II.5.5 | II.5.5 | EV-RES-05 / TC-RES-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
37 | RES-06 | View My Reservations | Reservation Management | Customer Screen / API | Customer | Lists the current customer's upcoming and historical reservations with status and summary information. | Only reservations owned by the authenticated customer are returned; sorting is deterministic. | Customer sees only own records; upcoming/history filters work; unauthorized ID guessing is blocked. | Iter2 | Iter2 | none | Nguyễn Đức Thương (DE190096) | High | Complex | 240 | Done | II.5.6 | II.5.6 | EV-RES-06 / TC-RES-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
38 | RES-07 | Reservation Detail | Reservation Management | Customer Screen / API | Customer | Shows one owned reservation with table, time, party, status, notes, and allowed actions. | Ownership is enforced server-side; actions depend on time and status. | Owned detail loads; other users receive 403/404; edit/cancel buttons appear only when allowed. | Iter2 | Iter2 | none | Nguyễn Đức Thương (DE190096) | Medium | Complex | 240 | Done | II.5.7 | II.5.7 | EV-RES-07 / TC-RES-07 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
39 | RES-08 | Update Future Reservation | Reservation Management | Customer API | Customer | Updates an eligible future reservation after rechecking capacity, table availability, time, and overlap. | Past, completed, cancelled, seated, or otherwise locked reservations cannot be modified. | Allowed changes persist and revalidate conflicts; forbidden statuses/times are rejected; original data remains on failure. | Iter2 | Iter2 | none | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Done | II.5.8 | II.5.8 | EV-RES-08 / TC-RES-08 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
40 | RES-09 | Cancel Reservation Rule | Reservation Management | Customer / Staff API | Customer, Staff | Cancels an eligible reservation while preserving the record and releasing table availability. | Cancellation is status/time dependent; cancellation reason may be required for staff actions. | Eligible cancellation updates status; repeated cancellation is idempotent; table becomes available when appropriate. | Iter2 | Iter2 | none | Trần Thanh Gia Huy (DE180571) | High | Medium | 120 | Done | II.5.9 | II.5.9 | EV-RES-09 / TC-RES-09 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
41 | RES-10 | Admin / Staff Reservation List | Reservation Management | Admin/Staff Screen / API | Admin, Staff | Provides paginated search and filters by customer, table, date range, and reservation status. | Access is role-restricted; date filters are inclusive and stable; sensitive customer fields are minimized. | Authorized users can find reservations accurately; non-authorized access is rejected; export scope is controlled if used. | Iter2 | Iter2 | Iter3 | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Updated | II.5.10 | II.5.10 | EV-RES-10 / TC-RES-10 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
42 | RES-11 | Confirm / Seat / Complete Reservation | Reservation Management | Staff API | Staff, Admin | Moves reservations through operational states and synchronizes the table state where required. | Only permitted transitions are allowed; seating requires an available assigned table; completion releases the table. | Valid transition sequence succeeds; skipped/reversed transitions fail; table status remains consistent. | Iter2 | Iter2 | Iter3 | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Updated | II.5.11 | II.5.11 | EV-RES-11 / TC-RES-11 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
43 | RES-12 | No-show / Expired Reservation Handling | Reservation Management | Staff Function | Staff, Admin | Marks eligible past reservations as no-show or expired according to operational policy. | Only past confirmed reservations qualify; changes are auditable and must not affect unrelated reservations. | Eligible records can be marked; future/already-final records are rejected; table availability is restored. | Iter2 | Iter2 | Iter4 | Trần Thanh Gia Huy (DE180571) | Medium | Medium | 120 | Updated | II.5.12 | II.5.12 | EV-RES-12 / TC-RES-12 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
44 | SYS-01 | Standard API Response & Validation Errors | System Foundation | Cross-cutting Backend | All Actors | Uses a common response/error structure for validation, business, authentication, authorization, and unexpected failures. | Error responses include stable code, message, timestamp, and field errors where applicable; stack traces are not exposed. | Representative APIs return the same format for success and each error class; frontend handles them without special-case crashes. | Iter2 | Iter2 | Iter4 | Phan Nguyễn (DE191019) | High | Complex | 240 | Updated | II.6.1 | II.6.1 | EV-SYS-01 / TC-SYS-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
45 | SYS-02 | Database Migration & Seed for Table / Reservation | System Foundation | Database Migration | Development Team | Provides ordered migration scripts and safe reference seed data for table and reservation modules. | Migrations run on a clean database and an existing development database; seed data uses deterministic keys and no secrets. | Flyway/migration history is successful; schema constraints/indexes exist; application starts with the clean database. | Iter2 | Iter2 | none | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Doing | II.6.2 | II.6.2 | EV-SYS-02 / TC-SYS-02 | Manual SQL/schema setup remains; no verified Flyway migration baseline. | Partial
46 | CART-01 | Add Item to Cart | Cart & Order Management | Customer UI | Customer | Adds an available menu item with selected quantity and notes to the customer's cart. | Only active/available items can be added; quantity is positive and within the configured maximum. | Valid item appears once with correct quantity; unavailable/invalid item is blocked; feedback is immediate. | Iter3 | Iter3 | none | Nguyễn Tiến Lộc (DE190986) | High | Medium | 120 | Doing | II.7.1 | II.7.1 | EV-CART-01 / TC-CART-01 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Partial
47 | CART-02 | Update Cart Quantity & Revalidate Availability | Cart & Order Management | Customer UI / Service | Customer | Changes cart item quantity and rechecks current food availability and price constraints. | Quantity cannot be zero/negative or exceed limit; unavailable items are flagged before checkout. | Valid quantity updates subtotal; invalid quantity is rejected; unavailable items cannot proceed unnoticed. | Iter3 | Iter3 | none | Nguyễn Tiến Lộc (DE190986) | High | Medium | 120 | Doing | II.7.2 | II.7.2 | EV-CART-02 / TC-CART-02 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Partial
48 | CART-03 | Remove Item / Clear Cart | Cart & Order Management | Customer UI | Customer | Removes one item or clears all cart items with confirmation where appropriate. | Removing/clearing affects only the current customer/session; operation is idempotent. | Selected item is removed; clear empties the cart; repeated actions do not cause errors. | Iter3 | Iter3 | none | Nguyễn Tiến Lộc (DE190986) | Medium | Simple | 60 | Doing | II.7.3 | II.7.3 | EV-CART-03 / TC-CART-03 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Partial
49 | CART-04 | Cart Subtotal Calculation | Cart & Order Management | Business Calculation | Customer | Calculates subtotal from current authoritative food price and quantity before discounts and payment. | Money uses DECIMAL precision; client-calculated totals are display-only and never trusted by order creation. | Subtotal matches server calculation for multiple items/quantities; decimal rounding follows policy. | Iter3 | Iter3 | none | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Doing | II.7.4 | II.7.4 | EV-CART-04 / TC-CART-04 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Partial
50 | CART-05 | Cart Persistence Across Navigation / Session | Cart & Order Management | Customer UI / Persistence | Customer | Preserves the cart across page navigation and expected session lifecycle while keeping it scoped to the current user. | One user's cart is never exposed to another; stale items are revalidated before checkout. | Cart survives expected navigation/refresh; logout/user switch does not leak items; stale data is handled. | Iter3 | Iter3 | none | Nguyễn Đức Thương (DE190096) | Medium | Complex | 240 | Doing | II.7.5 | II.7.5 | EV-CART-05 / TC-CART-05 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Partial
51 | ORDER-01 | Checkout Form & Order Notes | Cart & Order Management | Customer UI | Customer | Displays order summary and captures dining/table information, contact details, and order notes before submission. | Required fields depend on order type; notes have length limits; final values are revalidated by backend. | Customer can review accurate items/subtotal; invalid checkout data is blocked; submission occurs once. | Iter3 | Iter3 | none | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Done | II.8.1 | II.8.1 | EV-ORDER-01 / TC-ORDER-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
52 | ORDER-02 | Server-side Create Order Transaction | Cart & Order Management | Backend Service / DB | Customer, Staff | Creates order header and items atomically after validating identity, food availability, table/order type, and prices. | All items succeed or the transaction rolls back; order ownership/creator comes from authenticated context. | Successful order contains complete header/items; any invalid item causes full rollback; duplicate submission is controlled. | Iter3 | Iter3 | Iter4 | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Updated | II.8.2 | II.8.2 | EV-ORDER-02 / TC-ORDER-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
53 | ORDER-03 | Persist Order Items & Price Snapshot | Cart & Order Management | Database / Service | Customer, Staff | Stores each ordered item with quantity, unit price snapshot, notes, and relationship to the order. | Historical prices do not change when menu prices are edited; quantity and unit price are positive. | Order details reproduce the original order after menu updates; database relationships and totals reconcile. | Iter3 | Iter3 | none | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Done | II.8.3 | II.8.3 | EV-ORDER-03 / TC-ORDER-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
54 | ORDER-04 | Recalculate Final Total & Reject Client Manipulation | Cart & Order Management | Business Service | Customer, Staff | Recalculates subtotal, discount, and final amount from database values rather than accepting client totals. | Discount cannot exceed permitted amount; monetary fields use fixed precision; invalid coupon/payment state is rejected. | Manipulated client total is ignored; persisted total matches server calculation; tests cover rounding and invalid discounts. | Iter3 | Iter3 | Iter4 | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Done | II.8.4 | II.8.4 | EV-ORDER-04 / TC-ORDER-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
55 | ORDER-05 | View Own Order History | Cart & Order Management | Customer Screen / API | Customer | Lists current and previous orders for the authenticated customer with status, time, and amount summary. | Only owned orders are returned; pagination and sorting are deterministic. | Customer sees only own orders; status and totals match database; filters/no-data work. | Iter3 | Iter3 | none | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Done | II.8.5 | II.8.5 | EV-ORDER-05 / TC-ORDER-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
56 | ORDER-06 | View Own Order Detail | Cart & Order Management | Customer Screen / API | Customer | Displays order items, price breakdown, status history, payment/invoice availability, and notes. | Ownership is enforced; price breakdown comes from persisted authoritative values. | Owned order detail loads accurately; other customers cannot access it; invoice link appears only when issued. | Iter3 | Iter3 | none | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Done | II.8.6 | II.8.6 | EV-ORDER-06 / TC-ORDER-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
57 | ORDER-07 | Order Ownership Authorization | Cart & Order Management | Authorization Policy | Customer | Protects order history, detail, cancellation, payment, invoice, and feedback operations by authenticated ownership. | Customer cannot act on another customer's order; staff/admin access follows explicit operational roles. | ID-guessing tests return 403/404; authorized owner and allowed staff roles succeed. | Iter3 | Iter3 | none | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Done | II.8.7 | II.8.7 | EV-ORDER-07 / TC-ORDER-07 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
58 | ORDER-08 | Staff Counter Order Creation | Staff Operations | Staff Screen / API | Staff | Allows staff to create an order for walk-in or seated customers using live menu and optional table selection. | Staff identity is recorded; table must be eligible; unavailable foods and manipulated prices are rejected. | Staff can create a valid order; order appears in staff/kitchen flows; invalid table/item input rolls back. | Iter3 | Iter3 | none | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Done | II.8.8 | II.8.8 | EV-ORDER-08 / TC-ORDER-08 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
59 | ORDER-09 | Admin / Staff Order List & Filters | Staff Operations | Admin/Staff Screen / API | Admin, Staff | Provides order search and filters by date, status, customer, table, staff, and payment state. | Role restrictions and pagination apply; revenue-sensitive fields are limited to authorized roles. | Filters return correct orders; list updates after status/payment changes; non-authorized access is blocked. | Iter3 | Iter3 | Iter4 | Phan Nguyễn (DE191019) | High | Complex | 240 | Updated | II.8.9 | II.8.9 | EV-ORDER-09 / TC-ORDER-09 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
60 | ORDER-10 | Controlled Order Status Transitions | Staff Operations | Backend Service | Admin, Staff, Kitchen Staff | Moves orders through allowed states such as pending, confirmed, preparing, ready, served, completed, or cancelled. | Transitions follow a defined state machine; completed/cancelled orders are final except authorized correction policy. | Valid sequence succeeds; invalid jumps/reversal fail; kitchen/table/payment side effects remain consistent. | Iter3 | Iter3 | Iter4 | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Updated | II.8.10 | II.8.10 | EV-ORDER-10 / TC-ORDER-10 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
61 | STAFF-01 | Assign Tables to Staff | Staff Operations | Admin/Staff Screen / API | Admin, Staff | Creates time-bounded staff-to-table assignments used by the service workspace. | Staff/table must be active; assignment times are valid; assignment creator is auditable. | Valid assignment appears in workspace; invalid/inactive references are rejected; history is retained. | Iter3 | none | none | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Not Started | II.9.1 | II.9.1 | EV-STAFF-01 / TC-STAFF-01 | Employee/table-assignment persistence and conflict rules are not verified in the current repository. | Missing
62 | STAFF-02 | Prevent Active Assignment Conflict | Staff Operations | Business Service | Admin, Staff | Prevents overlapping active assignments that violate the configured one-table/one-staff service policy. | Conflict rules are evaluated transactionally and respect assignment end time/status. | Conflicting assignment is rejected; non-overlapping assignment succeeds; concurrent tests preserve consistency. | Iter3 | none | none | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Not Started | II.9.2 | II.9.2 | EV-STAFF-02 / TC-STAFF-02 | Employee/table-assignment persistence and conflict rules are not verified in the current repository. | Missing
63 | STAFF-03 | Staff Workspace / Assigned Tables | Staff Operations | Staff Screen | Staff | Shows the logged-in staff member's assigned tables, current reservations, and active orders. | Data is scoped to the authenticated staff member and current active assignments. | Staff sees only assigned work; updates reflect order/table status changes; empty state is usable. | Iter3 | Iter3 | none | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Doing | II.9.3 | II.9.3 | EV-STAFF-03 / TC-STAFF-03 | Staff-facing behavior exists only partially; complete API integration, authorization, and evidence. | Partial
64 | STAFF-04 | Cancel Order with Reason & Audit | Staff Operations | Staff/Admin API | Admin, Staff | Cancels an eligible order with a required reason and records who performed the action. | Paid/completed orders cannot be casually cancelled; cancellation must preserve historical order items and financial records. | Allowed cancellation records reason/actor/time; forbidden state is rejected; order remains visible in history. | Iter3 | Iter3 | Iter4 | Phan Nguyễn (DE191019) | High | Complex | 240 | Doing | II.9.4 | II.9.4 | EV-STAFF-04 / TC-STAFF-04 | Staff-facing behavior exists only partially; complete API integration, authorization, and evidence. | Partial
65 | KITCHEN-01 | Kitchen Order Queue | Kitchen Operations | Kitchen Screen / API | Kitchen Staff | Shows confirmed/preparing orders needing kitchen action, prioritized by time and operational status. | Only kitchen-relevant orders/items appear; access is role-restricted; ordering is deterministic. | Queue refreshes from live data; completed/cancelled items leave active queue; wrong roles are denied. | Iter3 | Iter3 | Iter4 | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Updated | II.10.1 | II.10.1 | EV-KITCHEN-01 / TC-KITCHEN-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
66 | KITCHEN-02 | Item-level Preparation Notes & Status | Kitchen Operations | Kitchen Screen / API | Kitchen Staff | Displays item notes and updates preparation status at item/order level according to the chosen workflow. | Kitchen cannot modify prices/customer data; status changes follow allowed preparation sequence. | Notes are visible; valid preparation updates persist; invalid transitions and unauthorized fields are rejected. | Iter3 | Iter3 | Iter4 | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Updated | II.10.2 | II.10.2 | EV-KITCHEN-02 / TC-KITCHEN-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
67 | KITCHEN-03 | Kitchen History Search & Filter | Kitchen Operations | Kitchen Screen / API | Kitchen Staff, Admin | Lists prepared, completed, and cancelled kitchen work with date/status/order filters. | History is read-only for finalized records; role restrictions and pagination apply. | Search/filter returns correct history; finalized data cannot be edited; empty results are handled. | Iter3 | Iter3 | none | Nguyễn Tiến Lộc (DE190986) | Medium | Medium | 120 | Done | II.10.3 | II.10.3 | EV-KITCHEN-03 / TC-KITCHEN-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
68 | KITCHEN-04 | Kitchen Access Authorization | Kitchen Operations | Authorization Policy | Kitchen Staff, Admin | Restricts kitchen queue and status actions to kitchen staff or explicitly authorized admin roles. | Customer/general staff tokens cannot call kitchen mutation APIs; read/write permissions are explicit. | Authorization tests prove correct role access and reject all disallowed roles. | Iter3 | Iter3 | none | Phạm Văn Quyết (DE190425) | Critical | Medium | 120 | Done | II.10.4 | II.10.4 | EV-KITCHEN-04 / TC-KITCHEN-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
69 | COUPON-01 | Coupon Entity & Database Migration | Coupon Management | Database Migration | Admin, Customer, Staff | Creates coupon and usage persistence with code, type, value, limits, validity period, status, and audit fields. | Coupon code is unique; values and dates are valid; monetary/percentage constraints and indexes are enforced. | Migration succeeds on a clean database; constraints reject invalid/duplicate records; entity mapping passes tests. | Iter4 | none | none | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Not Started | II.11.1 | II.11.1 | EV-COUPON-01 / TC-COUPON-01 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Missing
70 | COUPON-02 | Admin Coupon List / Create / Update | Coupon Management | Admin Screen / API | Admin | Provides secure coupon search, creation, editing, activation, and deactivation. | Only admin can mutate coupons; used coupons are not hard-deleted; overlapping validity and limits are validated. | Admin CRUD persists correctly; invalid/duplicate data is rejected; non-admin mutation returns 403. | Iter4 | none | none | Nguyễn Đức Thương (DE190096) | Critical | Complex | 240 | Not Started | II.11.2 | II.11.2 | EV-COUPON-02 / TC-COUPON-02 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Missing
71 | COUPON-03 | Coupon Eligibility Validation API | Coupon Management | Backend API | Customer, Staff | Validates coupon status, date, minimum amount, usage limits, role/customer eligibility, and applicable order context. | Validation uses server time/data; an invalid coupon cannot affect order total; error reasons are controlled. | Valid coupon returns authoritative discount preview; expired/inactive/over-limit/ineligible coupons are rejected. | Iter4 | none | none | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Not Started | II.11.3 | II.11.3 | EV-COUPON-03 / TC-COUPON-03 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Missing
72 | COUPON-04 | Apply Coupon Server-side to Order | Coupon Management | Business Service | Customer, Staff | Applies the validated coupon inside the order transaction and persists discount and final total. | Client discount values are ignored; discount cannot exceed subtotal; one coupon policy is enforced unless specified otherwise. | Persisted order total matches server calculation; manipulated requests fail; transaction rolls back on invalid coupon. | Iter4 | none | none | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Not Started | II.11.4 | II.11.4 | EV-COUPON-04 / TC-COUPON-04 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Missing
73 | COUPON-05 | Coupon Usage Limit & Atomic Persistence | Coupon Management | Database / Business Service | Customer, Staff | Records coupon usage atomically and enforces global/per-user usage limits during concurrent order creation. | Usage is counted only for the configured successful state; rollback removes failed usage; concurrency cannot exceed limits. | Concurrent final-usage tests allow only permitted usage; failed order creates no orphan usage record. | Iter4 | none | none | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Not Started | II.11.5 | II.11.5 | EV-COUPON-05 / TC-COUPON-05 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Missing
74 | PAY-01 | Payment Method Selection UI | Payment & Invoice | Customer / Staff UI | Customer, Staff | Allows selection of supported payment methods such as cash or QR and displays payable amount from the server. | UI cannot mark an order paid by itself; method availability follows order status and role. | Selected method is submitted to the payment API; displayed amount matches server; unsupported method is blocked. | Iter4 | Iter4 | none | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Doing | II.12.1 | II.12.1 | EV-PAY-01 / TC-PAY-01 | Payment selection/integration remains mixed; verify real PayOS/QR callback and persisted payment state. | Partial
75 | PAY-02 | Payment Processing API | Payment & Invoice | Backend API | Customer, Staff | Processes an eligible order payment request and returns an authoritative payment result. | Order must exist, be payable, and be owned/operated by an authorized actor; amount comes from the order. | Successful request creates payment; invalid order/state/role fails; API is covered for cash/QR outcomes. | Iter4 | Iter4 | none | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Done | II.12.2 | II.12.2 | EV-PAY-02 / TC-PAY-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
76 | PAY-03 | Payment Amount Verification & Idempotency | Payment & Invoice | Business Service | Customer, Staff | Verifies payment amount against the final order total and prevents duplicate processing of the same request/order. | Client amount is advisory only; idempotency key/order uniqueness prevents duplicate successful payments. | Amount mismatch fails; repeated request returns the original result or safe conflict; no duplicate records are created. | Iter4 | Iter4 | none | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Done | II.12.3 | II.12.3 | EV-PAY-03 / TC-PAY-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
77 | PAY-04 | Persist Payment & Complete Order Transactionally | Payment & Invoice | Backend Service / DB | Customer, Staff | Stores payment details and updates the order to completed only within one successful transaction. | Failed payment leaves order unpaid; one successful payment per order; state transition follows order rules. | Success creates one payment and completes order; failure rolls back; SQL evidence reconciles amount/status. | Iter4 | Iter4 | none | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Done | II.12.4 | II.12.4 | EV-PAY-04 / TC-PAY-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
78 | INV-01 | Invoice Entity & Unique Order Rule | Payment & Invoice | Database Migration | Customer, Staff, Admin | Creates immutable invoice persistence linked one-to-one with a successfully paid order. | One invoice per paid order; invoice number is unique; financial snapshot fields are non-editable after issue. | Migration creates constraints; duplicate invoice creation fails; invoice values remain unchanged after menu updates. | Iter4 | none | none | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Not Started | II.13.1 | II.13.1 | EV-INV-01 / TC-INV-01 | Invoice persistence/generation/download is planned and depends on a verified successful payment flow. | Missing
79 | INV-02 | Generate Immutable Invoice after Payment | Payment & Invoice | Backend Service | Customer, Staff | Generates the invoice automatically within/after the successful payment transaction using order and payment snapshots. | No invoice is generated for failed payment; retry cannot create a second invoice; totals reconcile exactly. | Each successful payment produces exactly one invoice; failed/duplicate payment produces none/one as appropriate. | Iter4 | none | none | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Not Started | II.13.2 | II.13.2 | EV-INV-02 / TC-INV-02 | Invoice persistence/generation/download is planned and depends on a verified successful payment flow. | Missing
80 | INV-03 | View / Download Invoice | Payment & Invoice | UI / Backend API | Customer, Staff, Admin | Allows authorized users to view invoice details and download/print a stable invoice representation. | Customer can access only own invoice; staff/admin access follows role; issued invoice is read-only. | Authorized view/download works; unauthorized access fails; displayed/PDF totals match database. | Iter4 | none | none | Phan Nguyễn (DE191019) | High | Complex | 240 | Not Started | II.13.3 | II.13.3 | EV-INV-03 / TC-INV-03 | Invoice persistence/generation/download is planned and depends on a verified successful payment flow. | Missing
81 | FB-01 | Submit Feedback Screen | Feedback Management | Customer UI | Customer | Collects rating and comment for an eligible completed order and displays validation/API responses. | Rating range and comment length are validated; UI alone does not persist final feedback. | Eligible customer can submit once; invalid rating/comment is blocked; refresh shows persisted result after backend completion. | Iter4 | Iter4 | none | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Doing | II.14.1 | II.14.1 | EV-FB-01 / TC-FB-01 | Frontend/backend integration or moderation evidence is incomplete; close with persistence and authorization proof. | Partial
82 | FB-02 | Feedback Persistence & Completed-order Eligibility | Feedback Management | Backend API / DB | Customer | Persists feedback only when the authenticated customer owns a completed eligible order. | Cancelled/unpaid/incomplete/other-user orders are ineligible; customer identity comes from authentication. | Eligible feedback remains after refresh; ineligible/unauthorized requests fail; database relation is correct. | Iter4 | Iter4 | none | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Done | II.14.2 | II.14.2 | EV-FB-02 / TC-FB-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
83 | FB-03 | One Feedback per Order & Input Validation | Feedback Management | Business Service / DB | Customer | Enforces one active feedback record per customer order and validates rating/comment. | Unique constraint prevents duplicates under concurrency; rating is within configured range; comment is sanitized/limited. | Duplicate/concurrent submissions create at most one record; invalid input returns field errors. | Iter4 | Iter4 | none | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Done | II.14.3 | II.14.3 | EV-FB-03 / TC-FB-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
84 | FB-04 | Admin Feedback Search / Moderation | Feedback Management | Admin Screen / API | Admin | Lists feedback with filters and permits controlled moderation status without rewriting the original rating history. | Only admin moderates; original author/rating/comment remain auditable; moderation action records actor/time/reason. | Admin can search/filter/review/moderate; non-admin is denied; moderation persists after refresh. | Iter4 | none | none | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Doing | II.14.4 | II.14.4 | EV-FB-04 / TC-FB-04 | Frontend/backend integration or moderation evidence is incomplete; close with persistence and authorization proof. | Partial
85 | RPT-01 | Dashboard KPI Aggregation API | Reporting & Analytics | Backend Report API | Admin | Calculates operational KPIs such as paid revenue, completed orders, active reservations, and customer counts from live data. | Revenue includes only successful paid/completed orders; cancelled/unpaid orders are excluded; date boundaries are explicit. | API values reconcile with direct SQL for the same period; empty period returns zero/no-data safely. | Iter4 | Iter4 | none | Phan Nguyễn (DE191019) | Critical | Complex | 240 | Done | II.15.1 | II.15.1 | EV-RPT-01 / TC-RPT-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
86 | RPT-02 | Revenue Trend & Date Filter | Reporting & Analytics | Backend API / Admin UI | Admin | Groups paid revenue by day/month and supports date-range filtering for dashboard charts. | Grouping uses consistent timezone; filters are inclusive as documented; only verified successful payments count. | Chart data matches SQL aggregation; changing date range refreshes correctly; empty ranges render safely. | Iter4 | Iter4 | none | Phan Nguyễn (DE191019) | High | Complex | 240 | Done | II.15.2 | II.15.2 | EV-RPT-02 / TC-RPT-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
87 | RPT-03 | Top Food & Order-status Reports | Reporting & Analytics | Backend API / Admin UI | Admin | Reports top-selling foods and order counts by status using persisted order items and orders. | Cancelled orders are excluded from sales ranking; historical item names/prices use snapshots where appropriate. | Rankings/counts reconcile with SQL; filters and tie handling are documented; non-admin access is blocked. | Iter4 | Iter4 | none | Phan Nguyễn (DE191019) | High | Complex | 240 | Done | II.15.3 | II.15.3 | EV-RPT-03 / TC-RPT-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
88 | RPT-04 | Dashboard Frontend Live-data Integration | Reporting & Analytics | Admin UI | Admin | Replaces hardcoded dashboard values with secured report API calls, loading states, errors, and no-data states. | No production metric remains hardcoded; requests include authentication; chart labels/units match API. | Network evidence shows real API calls; displayed totals match response/SQL; API failure does not crash page. | Iter4 | Iter4 | none | Nguyễn Đức Thương (DE190096) | Critical | Complex | 240 | Done | II.15.4 | II.15.4 | EV-RPT-04 / TC-RPT-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag. | Verified
89 | AI-01 | AI Analytics with Controlled Data & Logging | AI Support | Admin AI Function | Admin | Provides AI-assisted interpretation of selected report data with controlled inputs, advisory output, and audit logging. | AI output is advisory and cannot directly alter financial/operational data; prompts exclude secrets and unnecessary PII. | Authorized admin receives a logged result; failures have safe fallback; output clearly states limitations. | Iter4 | Iter4 | none | Trần Thanh Gia Huy (DE180571) | Medium | Complex | 240 | Doing | II.16.1 | II.16.1 | EV-AI-01 / TC-AI-01 | Experimental/prototype capability only; advisory scope, safe fallback, logging, and live-server evidence must be demonstrated. | Experimental
90 | AI-02 | Customer Chatbot FAQ & Safe Fallback | AI Support | Customer AI Function | Guest, Customer | Answers common restaurant/menu/reservation/order questions and routes unsupported requests to a safe fallback. | Chatbot cannot expose another user's data or perform privileged actions without authenticated APIs; uncertain answers are disclosed. | FAQ answers are relevant; unsafe/unknown prompts receive fallback; session-aware links do not leak data. | Iter4 | Iter4 | none | Trần Thanh Gia Huy (DE180571) | Medium | Complex | 240 | Doing | II.16.2 | II.16.2 | EV-AI-02 / TC-AI-02 | Experimental/prototype capability only; advisory scope, safe fallback, logging, and live-server evidence must be demonstrated. | Experimental

## Iter1
PROJECTSWP – ITER1 TRACKING
25 detailed functions ¦ Ownership is balanced across the semester ¦ All functions require SRS, SDS, code/test evidence, and final release traceability.
Use this sheet for iteration demo preparation: verify status, acceptance criteria, evidence IDs, and update notes before tagging the release.
No. | Work ID | Screen / Function | Feature | Type | Actor | Detailed Description | In Charge | Priority | Complexity | Target LOC | Planned Week | Status | SRS Ref | SDS Ref | Acceptance Criteria | Evidence ID / Test ID | Notes
1 | AUTH-01 | Login Screen & Client Validation | Authentication & Security | UI Screen | Guest, All Users | Presents email/password fields, validates required format, shows field-level errors, and redirects authenticated users to the correct role workspace. | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Week 1 | Done | II.1.1 | II.1.1 | Valid input submits once; invalid input remains on screen with clear messages; successful login redirects by role without exposing credentials. | EV-AUTH-01 / TC-AUTH-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
2 | AUTH-02 | Credential Authentication API | Authentication & Security | Backend API | Guest | Authenticates a submitted email and password against an active user account and returns a standardized success or failure response. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 1 | Done | II.1.2 | II.1.2 | Correct credentials succeed; wrong password, unknown email, and inactive account return safe errors; API contract is covered by tests. | EV-AUTH-02 / TC-AUTH-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
3 | AUTH-03 | Password Hashing & Credential Verification | Authentication & Security | Security Service | Guest, All Users | Encodes passwords before persistence and verifies credentials through the configured password encoder. | Phạm Văn Quyết (DE190425) | Critical | Medium | 120 | Week 1 | Done | II.1.3 | II.1.3 | Database contains only encoded passwords; registration/reset/login use the same encoder; negative password tests pass. | EV-AUTH-03 / TC-AUTH-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
4 | AUTH-04 | JWT Access Token Generation | Authentication & Security | Security Service | Authenticated Users | Creates a signed access token containing the user identity, role claims, issue time, and expiration after successful authentication. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 2 | Done | II.1.4 | II.1.4 | A valid login returns a signed token; signature and expiration can be verified; tampered tokens are rejected. | EV-AUTH-04 / TC-AUTH-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
5 | AUTH-05 | JWT Refresh Token Persistence | Authentication & Security | Backend Service / DB | Authenticated Users | Stores refresh-token hashes and lifecycle metadata so an expired access token can be renewed without re-entering credentials. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 2 | Done | II.1.5 | II.1.5 | Valid refresh creates a new access token; expired/revoked/reused tokens fail; raw refresh tokens are not persisted. | EV-AUTH-05 / TC-AUTH-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
6 | AUTH-06 | JWT Authentication Filter | Authentication & Security | Security Filter | Authenticated Users | Reads the bearer token on every protected request, validates it, and populates the authenticated security context. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 2 | Done | II.1.6 | II.1.6 | Protected requests with valid tokens reach controllers; missing/invalid/expired tokens return 401; public routes remain accessible. | EV-AUTH-06 / TC-AUTH-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
7 | AUTH-07 | Token Expiry & Invalid Token Handling | Authentication & Security | Exception Handling | Authenticated Users | Returns consistent error responses for expired, malformed, unsupported, or incorrectly signed tokens. | Phạm Văn Quyết (DE190425) | Critical | Medium | 120 | Week 2 | Done | II.1.7 | II.1.7 | Each invalid-token scenario returns the expected HTTP status and message; frontend can distinguish expiry from authorization failure. | EV-AUTH-07 / TC-AUTH-07 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
8 | AUTH-08 | Endpoint Role Authorization Matrix | Authentication & Security | Authorization Policy | Admin, Staff, Kitchen Staff, Customer | Defines explicit access rules for all protected API groups and matches them with frontend role navigation. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 2 | Done | II.1.8 | II.1.8 | Authorization tests prove 401 for unauthenticated and 403 for wrong-role requests across representative endpoints. | EV-AUTH-08 / TC-AUTH-08 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
9 | AUTH-09 | Standard 401/403 Security Responses | Authentication & Security | Exception Handling | All Users | Converts authentication and authorization failures into predictable JSON responses consumed by the frontend. | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Week 2 | Done | II.1.9 | II.1.9 | Frontend receives stable error codes/messages; no HTML error page is returned by secured APIs; tests cover both statuses. | EV-AUTH-09 / TC-AUTH-09 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
10 | AUTH-10 | Logout & Token Revocation | Authentication & Security | Backend API | Authenticated Users | Ends an authenticated session by revoking the current refresh token and clearing client authentication state. | Phạm Văn Quyết (DE190425) | High | Medium | 120 | Week 2 | Done | II.1.10 | II.1.10 | After logout, refresh fails and protected requests require a new login; repeated logout requests do not create errors. | EV-AUTH-10 / TC-AUTH-10 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
11 | AUTH-11 | Registration Screen & Validation | Authentication & Security | UI Screen | Guest | Collects customer account information, validates required fields and password confirmation, and displays API validation errors. | Phan Nguyễn (DE191019) | High | Medium | 120 | Week 1 | Done | II.1.11 | II.1.11 | Valid data creates an account; invalid fields show messages; duplicate email feedback is shown without page crash. | EV-AUTH-11 / TC-AUTH-11 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
12 | AUTH-12 | Registration API & Duplicate Email Check | Authentication & Security | Backend API | Guest | Creates a customer account with the default role after validating input and uniqueness constraints. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 1 | Done | II.1.12 | II.1.12 | New account is persisted with customer role; duplicate email and invalid input are rejected; tests verify role protection. | EV-AUTH-12 / TC-AUTH-12 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
13 | AUTH-13 | Forgot Password Request | Authentication & Security | UI / Backend API | Guest | Allows a user to request a reset token or code without revealing whether the submitted email is registered. | Nguyễn Đức Thương (DE190096) | Medium | Complex | 240 | Week 2 | Done | II.1.13 | II.1.13 | Request always returns a safe response; valid accounts receive a usable reset token/code; repeated abuse is handled. | EV-AUTH-13 / TC-AUTH-13 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
14 | AUTH-14 | Reset Password Token Validation | Authentication & Security | Backend API | Guest | Validates the reset token/code, saves a new encoded password, and invalidates the token after successful use. | Phạm Văn Quyết (DE190425) | High | Complex | 240 | Week 2 | Done | II.1.14 | II.1.14 | Valid token updates the password once; old password stops working; expired/reused token tests pass. | EV-AUTH-14 / TC-AUTH-14 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
15 | USER-01 | View Own Profile | User Management | UI / Backend API | Customer, Staff, Kitchen Staff, Admin | Displays the authenticated user's profile and contact information using the current security identity. | Phan Nguyễn (DE191019) | Medium | Complex | 240 | Week 2 | Done | II.2.1 | II.2.1 | Profile loads after login, contains only permitted fields, and rejects attempts to read another user's data. | EV-USER-01 / TC-USER-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
16 | USER-02 | Update Own Profile | User Management | UI / Backend API | Customer, Staff, Kitchen Staff, Admin | Allows permitted personal/contact fields and avatar data to be updated while preserving role, status, and credentials. | Nguyễn Đức Thương (DE190096) | High | Complex | 240 | Week 2 | Updated | II.2.2 | II.2.2 | Permitted changes persist after refresh; protected-field tampering is ignored/rejected; validation messages are clear. | EV-USER-02 / TC-USER-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
17 | USER-03 | Admin User List & Search | User Management | Admin Screen / API | Admin | Provides paginated account listing with search and filters by role and account status. | Nguyễn Đức Thương (DE190096) | Critical | Complex | 240 | Week 2 | Done | II.2.3 | II.2.3 | Admin can load, search, filter, and open account details; non-admin requests return 403; empty results are handled. | EV-USER-03 / TC-USER-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
18 | USER-04 | Admin Change Role / Lock Account | User Management | Admin API | Admin | Allows safe role updates and account activation/locking with protection for critical accounts and active sessions. | Phan Nguyễn (DE191019) | Critical | Complex | 240 | Week 2 | Done | II.2.4 | II.2.4 | Allowed changes persist and affect authorization; unsafe changes are blocked; account lock prevents login immediately. | EV-USER-04 / TC-USER-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
19 | MENU-01 | Category List | Menu Management | Admin Screen / API | Admin | Lists categories with status, search, and item usage information for administration. | Phan Nguyễn (DE191019) | Medium | Medium | 120 | Week 1 | Done | II.3.1 | II.3.1 | Admin can search and filter categories; list reflects database state and handles no-data cases. | EV-MENU-01 / TC-MENU-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
20 | MENU-02 | Create / Update Category | Menu Management | Admin Screen / API | Admin | Creates and edits menu categories with normalized names and optional descriptions. | Phan Nguyễn (DE191019) | High | Medium | 120 | Week 1 | Done | II.3.2 | II.3.2 | Create/update persists valid data; duplicates and blank names are rejected with clear feedback. | EV-MENU-02 / TC-MENU-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
21 | MENU-03 | Deactivate Category & Referential Rule | Menu Management | Admin API | Admin | Deactivates a category while preserving historical references and preventing unsafe deletion when foods still depend on it. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 1 | Done | II.3.3 | II.3.3 | Deactivation is safe and reversible; existing historical food/order data remains valid. | EV-MENU-03 / TC-MENU-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
22 | MENU-04 | Admin Food List / Search / Filter | Menu Management | Admin Screen / API | Admin | Lists foods with category, price, availability, status, and keyword/category filters. | Phan Nguyễn (DE191019) | High | Medium | 120 | Week 1 | Updated | II.3.4 | II.3.4 | Search/filter results are correct; list refreshes after changes; no-data and API-error states are shown. | EV-MENU-04 / TC-MENU-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
23 | MENU-05 | Create / Update Food Item | Menu Management | Admin Screen / API | Admin | Creates and edits food name, category, price, description, image reference, status, and availability. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 1 | Updated | II.3.5 | II.3.5 | Valid foods persist and appear in the proper menu; invalid price/category/data are rejected; updates preserve order history snapshots. | EV-MENU-05 / TC-MENU-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
24 | MENU-06 | Food Image & Availability Management | Menu Management | UI / Backend API | Admin | Updates food image metadata and operational availability separately from active master-data status. | Nguyễn Đức Thương (DE190096) | High | Complex | 240 | Week 2 | Updated | II.3.6 | II.3.6 | Image/availability changes persist; customer menu updates; unavailable item ordering is blocked server-side. | EV-MENU-06 / TC-MENU-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
25 | MENU-07 | Customer Menu Browse / Detail / Filter | Menu Management | Customer Screen | Guest, Customer | Displays active available foods grouped by category with details, keyword search, and category filtering. | Phan Nguyễn (DE191019) | High | Medium | 120 | Week 2 | Done | II.3.7 | II.3.7 | Customer can browse and filter live menu data; unavailable items are hidden/disabled; cart entry points work. | EV-MENU-07 / TC-MENU-07 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.

## Iter2
PROJECTSWP – ITER2 TRACKING
20 detailed functions ¦ Ownership is balanced across the semester ¦ All functions require SRS, SDS, code/test evidence, and final release traceability.
Use this sheet for iteration demo preparation: verify status, acceptance criteria, evidence IDs, and update notes before tagging the release.
No. | Work ID | Screen / Function | Feature | Type | Actor | Detailed Description | In Charge | Priority | Complexity | Target LOC | Planned Week | Status | SRS Ref | SDS Ref | Acceptance Criteria | Evidence ID / Test ID | Notes
1 | TABLE-01 | View Table List & Availability | Table Management | UI / Backend API | Customer, Staff, Admin | Displays restaurant tables with table number, capacity, status, and availability appropriate to the current role. | Nguyễn Đức Thương (DE190096) | High | Complex | 240 | Week 1 | Done | II.4.1 | II.4.1 | Role-appropriate table data loads correctly; statuses match database state; no-data and error states are handled. | EV-TABLE-01 / TC-TABLE-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
2 | TABLE-02 | Admin Create / Update Table | Table Management | Admin Screen / API | Admin | Creates and edits restaurant table master data including number, capacity, status, and active flag. | Phạm Văn Quyết (DE190425) | High | Complex | 240 | Week 1 | Updated | II.4.2 | II.4.2 | Valid changes persist; duplicates and invalid capacity are rejected; updates appear in reservation/staff screens. | EV-TABLE-02 / TC-TABLE-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
3 | TABLE-03 | Table Capacity Validation | Table Management | Business Service | Admin, Staff, Customer | Validates table capacity during table maintenance, reservation matching, and staff assignment. | Phạm Văn Quyết (DE190425) | High | Medium | 120 | Week 1 | Done | II.4.3 | II.4.3 | Invalid capacity and oversized party selections are rejected consistently in UI and API tests. | EV-TABLE-03 / TC-TABLE-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
4 | TABLE-04 | Table Number Uniqueness | Table Management | Database / Service Validation | Admin | Prevents duplicate table numbers through service validation and a database uniqueness constraint. | Phan Nguyễn (DE191019) | High | Medium | 120 | Week 1 | Done | II.4.4 | II.4.4 | Duplicate requests return a conflict/validation error and only one table record exists after concurrent tests. | EV-TABLE-04 / TC-TABLE-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
5 | TABLE-05 | Table Operational Status Update | Table Management | Staff / Admin API | Staff, Admin | Updates operational table state such as available, reserved, occupied, or unavailable with controlled transitions. | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Week 2 | Updated | II.4.5 | II.4.5 | Allowed transitions succeed; invalid transitions return business errors; reservation/order flows remain synchronized. | EV-TABLE-05 / TC-TABLE-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
6 | TABLE-06 | Table Search & Filter | Table Management | UI / Backend API | Staff, Admin | Supports search and filtering by table number, capacity, active flag, and operational status. | Trần Thanh Gia Huy (DE180571) | Medium | Complex | 240 | Week 2 | Done | II.4.6 | II.4.6 | Combined filters return correct records and reset correctly; empty results display cleanly. | EV-TABLE-06 / TC-TABLE-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
7 | RES-01 | Create Reservation Form | Reservation Management | Customer Screen | Customer | Collects reservation date, time, party size, selected table, and optional notes with clear validation. | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Week 1 | Done | II.5.1 | II.5.1 | Valid form submits once; invalid date/time/party/table shows clear messages; success displays reservation details. | EV-RES-01 / TC-RES-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
8 | RES-02 | Search Available Tables | Reservation Management | Backend API | Customer, Staff | Returns tables available for a requested time range and party size. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 1 | Updated | II.5.2 | II.5.2 | Results match direct database checks; unavailable tables are never returned; boundary times are tested. | EV-RES-02 / TC-RES-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
9 | RES-03 | Reservation Capacity Matching | Reservation Management | Business Service | Customer, Staff | Matches party size with eligible table capacity and validates a manually selected table before saving. | Phạm Văn Quyết (DE190425) | High | Medium | 120 | Week 1 | Done | II.5.3 | II.5.3 | Oversized reservations are rejected server-side; valid matching returns appropriate tables. | EV-RES-03 / TC-RES-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
10 | RES-04 | Reservation Overlap & Concurrency Prevention | Reservation Management | Business Service / DB Lock | Customer, Staff | Prevents two active reservations from occupying the same table during overlapping time ranges, including concurrent submissions. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 1 | Updated | II.5.4 | II.5.4 | Sequential and concurrent overlap tests allow only one conflicting reservation; non-overlapping reservations succeed. | EV-RES-04 / TC-RES-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
11 | RES-05 | Reservation Persistence Transaction | Reservation Management | Backend Service / DB | Customer, Staff | Creates the reservation atomically after revalidating user, table, time, capacity, and overlap rules. | Phạm Văn Quyết (DE190425) | High | Complex | 240 | Week 1 | Done | II.5.5 | II.5.5 | Successful reservation has complete data; failures create no partial record; ownership is correct. | EV-RES-05 / TC-RES-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
12 | RES-06 | View My Reservations | Reservation Management | Customer Screen / API | Customer | Lists the current customer's upcoming and historical reservations with status and summary information. | Nguyễn Đức Thương (DE190096) | High | Complex | 240 | Week 2 | Done | II.5.6 | II.5.6 | Customer sees only own records; upcoming/history filters work; unauthorized ID guessing is blocked. | EV-RES-06 / TC-RES-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
13 | RES-07 | Reservation Detail | Reservation Management | Customer Screen / API | Customer | Shows one owned reservation with table, time, party, status, notes, and allowed actions. | Nguyễn Đức Thương (DE190096) | Medium | Complex | 240 | Week 2 | Done | II.5.7 | II.5.7 | Owned detail loads; other users receive 403/404; edit/cancel buttons appear only when allowed. | EV-RES-07 / TC-RES-07 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
14 | RES-08 | Update Future Reservation | Reservation Management | Customer API | Customer | Updates an eligible future reservation after rechecking capacity, table availability, time, and overlap. | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Week 2 | Done | II.5.8 | II.5.8 | Allowed changes persist and revalidate conflicts; forbidden statuses/times are rejected; original data remains on failure. | EV-RES-08 / TC-RES-08 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
15 | RES-09 | Cancel Reservation Rule | Reservation Management | Customer / Staff API | Customer, Staff | Cancels an eligible reservation while preserving the record and releasing table availability. | Trần Thanh Gia Huy (DE180571) | High | Medium | 120 | Week 2 | Done | II.5.9 | II.5.9 | Eligible cancellation updates status; repeated cancellation is idempotent; table becomes available when appropriate. | EV-RES-09 / TC-RES-09 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
16 | RES-10 | Admin / Staff Reservation List | Reservation Management | Admin/Staff Screen / API | Admin, Staff | Provides paginated search and filters by customer, table, date range, and reservation status. | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Week 2 | Updated | II.5.10 | II.5.10 | Authorized users can find reservations accurately; non-authorized access is rejected; export scope is controlled if used. | EV-RES-10 / TC-RES-10 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
17 | RES-11 | Confirm / Seat / Complete Reservation | Reservation Management | Staff API | Staff, Admin | Moves reservations through operational states and synchronizes the table state where required. | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Week 2 | Updated | II.5.11 | II.5.11 | Valid transition sequence succeeds; skipped/reversed transitions fail; table status remains consistent. | EV-RES-11 / TC-RES-11 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
18 | RES-12 | No-show / Expired Reservation Handling | Reservation Management | Staff Function | Staff, Admin | Marks eligible past reservations as no-show or expired according to operational policy. | Trần Thanh Gia Huy (DE180571) | Medium | Medium | 120 | Week 2 | Updated | II.5.12 | II.5.12 | Eligible records can be marked; future/already-final records are rejected; table availability is restored. | EV-RES-12 / TC-RES-12 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
19 | SYS-01 | Standard API Response & Validation Errors | System Foundation | Cross-cutting Backend | All Actors | Uses a common response/error structure for validation, business, authentication, authorization, and unexpected failures. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 1 | Updated | II.6.1 | II.6.1 | Representative APIs return the same format for success and each error class; frontend handles them without special-case crashes. | EV-SYS-01 / TC-SYS-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
20 | SYS-02 | Database Migration & Seed for Table / Reservation | System Foundation | Database Migration | Development Team | Provides ordered migration scripts and safe reference seed data for table and reservation modules. | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Week 1 | Doing | II.6.2 | II.6.2 | Flyway/migration history is successful; schema constraints/indexes exist; application starts with the clean database. | EV-SYS-02 / TC-SYS-02 | Manual SQL/schema setup remains; no verified Flyway migration baseline.

## Iter3
PROJECTSWP – ITER3 TRACKING
23 detailed functions ¦ Ownership is balanced across the semester ¦ All functions require SRS, SDS, code/test evidence, and final release traceability.
Use this sheet for iteration demo preparation: verify status, acceptance criteria, evidence IDs, and update notes before tagging the release.
No. | Work ID | Screen / Function | Feature | Type | Actor | Detailed Description | In Charge | Priority | Complexity | Target LOC | Planned Week | Status | SRS Ref | SDS Ref | Acceptance Criteria | Evidence ID / Test ID | Notes
1 | CART-01 | Add Item to Cart | Cart & Order Management | Customer UI | Customer | Adds an available menu item with selected quantity and notes to the customer's cart. | Nguyễn Tiến Lộc (DE190986) | High | Medium | 120 | Week 1 | Doing | II.7.1 | II.7.1 | Valid item appears once with correct quantity; unavailable/invalid item is blocked; feedback is immediate. | EV-CART-01 / TC-CART-01 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
2 | CART-02 | Update Cart Quantity & Revalidate Availability | Cart & Order Management | Customer UI / Service | Customer | Changes cart item quantity and rechecks current food availability and price constraints. | Nguyễn Tiến Lộc (DE190986) | High | Medium | 120 | Week 1 | Doing | II.7.2 | II.7.2 | Valid quantity updates subtotal; invalid quantity is rejected; unavailable items cannot proceed unnoticed. | EV-CART-02 / TC-CART-02 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
3 | CART-03 | Remove Item / Clear Cart | Cart & Order Management | Customer UI | Customer | Removes one item or clears all cart items with confirmation where appropriate. | Nguyễn Tiến Lộc (DE190986) | Medium | Simple | 60 | Week 1 | Doing | II.7.3 | II.7.3 | Selected item is removed; clear empties the cart; repeated actions do not cause errors. | EV-CART-03 / TC-CART-03 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
4 | CART-04 | Cart Subtotal Calculation | Cart & Order Management | Business Calculation | Customer | Calculates subtotal from current authoritative food price and quantity before discounts and payment. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 1 | Doing | II.7.4 | II.7.4 | Subtotal matches server calculation for multiple items/quantities; decimal rounding follows policy. | EV-CART-04 / TC-CART-04 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
5 | CART-05 | Cart Persistence Across Navigation / Session | Cart & Order Management | Customer UI / Persistence | Customer | Preserves the cart across page navigation and expected session lifecycle while keeping it scoped to the current user. | Nguyễn Đức Thương (DE190096) | Medium | Complex | 240 | Week 1 | Doing | II.7.5 | II.7.5 | Cart survives expected navigation/refresh; logout/user switch does not leak items; stale data is handled. | EV-CART-05 / TC-CART-05 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
6 | ORDER-01 | Checkout Form & Order Notes | Cart & Order Management | Customer UI | Customer | Displays order summary and captures dining/table information, contact details, and order notes before submission. | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Week 1 | Done | II.8.1 | II.8.1 | Customer can review accurate items/subtotal; invalid checkout data is blocked; submission occurs once. | EV-ORDER-01 / TC-ORDER-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
7 | ORDER-02 | Server-side Create Order Transaction | Cart & Order Management | Backend Service / DB | Customer, Staff | Creates order header and items atomically after validating identity, food availability, table/order type, and prices. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 1 | Updated | II.8.2 | II.8.2 | Successful order contains complete header/items; any invalid item causes full rollback; duplicate submission is controlled. | EV-ORDER-02 / TC-ORDER-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
8 | ORDER-03 | Persist Order Items & Price Snapshot | Cart & Order Management | Database / Service | Customer, Staff | Stores each ordered item with quantity, unit price snapshot, notes, and relationship to the order. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 1 | Done | II.8.3 | II.8.3 | Order details reproduce the original order after menu updates; database relationships and totals reconcile. | EV-ORDER-03 / TC-ORDER-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
9 | ORDER-04 | Recalculate Final Total & Reject Client Manipulation | Cart & Order Management | Business Service | Customer, Staff | Recalculates subtotal, discount, and final amount from database values rather than accepting client totals. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 2 | Done | II.8.4 | II.8.4 | Manipulated client total is ignored; persisted total matches server calculation; tests cover rounding and invalid discounts. | EV-ORDER-04 / TC-ORDER-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
10 | ORDER-05 | View Own Order History | Cart & Order Management | Customer Screen / API | Customer | Lists current and previous orders for the authenticated customer with status, time, and amount summary. | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Week 2 | Done | II.8.5 | II.8.5 | Customer sees only own orders; status and totals match database; filters/no-data work. | EV-ORDER-05 / TC-ORDER-05 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
11 | ORDER-06 | View Own Order Detail | Cart & Order Management | Customer Screen / API | Customer | Displays order items, price breakdown, status history, payment/invoice availability, and notes. | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Week 2 | Done | II.8.6 | II.8.6 | Owned order detail loads accurately; other customers cannot access it; invoice link appears only when issued. | EV-ORDER-06 / TC-ORDER-06 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
12 | ORDER-07 | Order Ownership Authorization | Cart & Order Management | Authorization Policy | Customer | Protects order history, detail, cancellation, payment, invoice, and feedback operations by authenticated ownership. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 2 | Done | II.8.7 | II.8.7 | ID-guessing tests return 403/404; authorized owner and allowed staff roles succeed. | EV-ORDER-07 / TC-ORDER-07 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
13 | ORDER-08 | Staff Counter Order Creation | Staff Operations | Staff Screen / API | Staff | Allows staff to create an order for walk-in or seated customers using live menu and optional table selection. | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Week 1 | Done | II.8.8 | II.8.8 | Staff can create a valid order; order appears in staff/kitchen flows; invalid table/item input rolls back. | EV-ORDER-08 / TC-ORDER-08 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
14 | ORDER-09 | Admin / Staff Order List & Filters | Staff Operations | Admin/Staff Screen / API | Admin, Staff | Provides order search and filters by date, status, customer, table, staff, and payment state. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 2 | Updated | II.8.9 | II.8.9 | Filters return correct orders; list updates after status/payment changes; non-authorized access is blocked. | EV-ORDER-09 / TC-ORDER-09 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
15 | ORDER-10 | Controlled Order Status Transitions | Staff Operations | Backend Service | Admin, Staff, Kitchen Staff | Moves orders through allowed states such as pending, confirmed, preparing, ready, served, completed, or cancelled. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 2 | Updated | II.8.10 | II.8.10 | Valid sequence succeeds; invalid jumps/reversal fail; kitchen/table/payment side effects remain consistent. | EV-ORDER-10 / TC-ORDER-10 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
16 | STAFF-01 | Assign Tables to Staff | Staff Operations | Admin/Staff Screen / API | Admin, Staff | Creates time-bounded staff-to-table assignments used by the service workspace. | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Week 1 | Not Started | II.9.1 | II.9.1 | Valid assignment appears in workspace; invalid/inactive references are rejected; history is retained. | EV-STAFF-01 / TC-STAFF-01 | Employee/table-assignment persistence and conflict rules are not verified in the current repository.
17 | STAFF-02 | Prevent Active Assignment Conflict | Staff Operations | Business Service | Admin, Staff | Prevents overlapping active assignments that violate the configured one-table/one-staff service policy. | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Week 1 | Not Started | II.9.2 | II.9.2 | Conflicting assignment is rejected; non-overlapping assignment succeeds; concurrent tests preserve consistency. | EV-STAFF-02 / TC-STAFF-02 | Employee/table-assignment persistence and conflict rules are not verified in the current repository.
18 | STAFF-03 | Staff Workspace / Assigned Tables | Staff Operations | Staff Screen | Staff | Shows the logged-in staff member's assigned tables, current reservations, and active orders. | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Week 2 | Doing | II.9.3 | II.9.3 | Staff sees only assigned work; updates reflect order/table status changes; empty state is usable. | EV-STAFF-03 / TC-STAFF-03 | Staff-facing behavior exists only partially; complete API integration, authorization, and evidence.
19 | STAFF-04 | Cancel Order with Reason & Audit | Staff Operations | Staff/Admin API | Admin, Staff | Cancels an eligible order with a required reason and records who performed the action. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 2 | Doing | II.9.4 | II.9.4 | Allowed cancellation records reason/actor/time; forbidden state is rejected; order remains visible in history. | EV-STAFF-04 / TC-STAFF-04 | Staff-facing behavior exists only partially; complete API integration, authorization, and evidence.
20 | KITCHEN-01 | Kitchen Order Queue | Kitchen Operations | Kitchen Screen / API | Kitchen Staff | Shows confirmed/preparing orders needing kitchen action, prioritized by time and operational status. | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Week 1 | Updated | II.10.1 | II.10.1 | Queue refreshes from live data; completed/cancelled items leave active queue; wrong roles are denied. | EV-KITCHEN-01 / TC-KITCHEN-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
21 | KITCHEN-02 | Item-level Preparation Notes & Status | Kitchen Operations | Kitchen Screen / API | Kitchen Staff | Displays item notes and updates preparation status at item/order level according to the chosen workflow. | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Week 1 | Updated | II.10.2 | II.10.2 | Notes are visible; valid preparation updates persist; invalid transitions and unauthorized fields are rejected. | EV-KITCHEN-02 / TC-KITCHEN-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
22 | KITCHEN-03 | Kitchen History Search & Filter | Kitchen Operations | Kitchen Screen / API | Kitchen Staff, Admin | Lists prepared, completed, and cancelled kitchen work with date/status/order filters. | Nguyễn Tiến Lộc (DE190986) | Medium | Medium | 120 | Week 2 | Done | II.10.3 | II.10.3 | Search/filter returns correct history; finalized data cannot be edited; empty results are handled. | EV-KITCHEN-03 / TC-KITCHEN-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
23 | KITCHEN-04 | Kitchen Access Authorization | Kitchen Operations | Authorization Policy | Kitchen Staff, Admin | Restricts kitchen queue and status actions to kitchen staff or explicitly authorized admin roles. | Phạm Văn Quyết (DE190425) | Critical | Medium | 120 | Week 2 | Done | II.10.4 | II.10.4 | Authorization tests prove correct role access and reject all disallowed roles. | EV-KITCHEN-04 / TC-KITCHEN-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.

## Iter4
PROJECTSWP – ITER4 TRACKING
22 detailed functions ¦ Ownership is balanced across the semester ¦ All functions require SRS, SDS, code/test evidence, and final release traceability.
Use this sheet for iteration demo preparation: verify status, acceptance criteria, evidence IDs, and update notes before tagging the release.
No. | Work ID | Screen / Function | Feature | Type | Actor | Detailed Description | In Charge | Priority | Complexity | Target LOC | Planned Week | Status | SRS Ref | SDS Ref | Acceptance Criteria | Evidence ID / Test ID | Notes
1 | COUPON-01 | Coupon Entity & Database Migration | Coupon Management | Database Migration | Admin, Customer, Staff | Creates coupon and usage persistence with code, type, value, limits, validity period, status, and audit fields. | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Week 1 | Not Started | II.11.1 | II.11.1 | Migration succeeds on a clean database; constraints reject invalid/duplicate records; entity mapping passes tests. | EV-COUPON-01 / TC-COUPON-01 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
2 | COUPON-02 | Admin Coupon List / Create / Update | Coupon Management | Admin Screen / API | Admin | Provides secure coupon search, creation, editing, activation, and deactivation. | Nguyễn Đức Thương (DE190096) | Critical | Complex | 240 | Week 1 | Not Started | II.11.2 | II.11.2 | Admin CRUD persists correctly; invalid/duplicate data is rejected; non-admin mutation returns 403. | EV-COUPON-02 / TC-COUPON-02 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
3 | COUPON-03 | Coupon Eligibility Validation API | Coupon Management | Backend API | Customer, Staff | Validates coupon status, date, minimum amount, usage limits, role/customer eligibility, and applicable order context. | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Week 1 | Not Started | II.11.3 | II.11.3 | Valid coupon returns authoritative discount preview; expired/inactive/over-limit/ineligible coupons are rejected. | EV-COUPON-03 / TC-COUPON-03 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
4 | COUPON-04 | Apply Coupon Server-side to Order | Coupon Management | Business Service | Customer, Staff | Applies the validated coupon inside the order transaction and persists discount and final total. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 1 | Not Started | II.11.4 | II.11.4 | Persisted order total matches server calculation; manipulated requests fail; transaction rolls back on invalid coupon. | EV-COUPON-04 / TC-COUPON-04 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
5 | COUPON-05 | Coupon Usage Limit & Atomic Persistence | Coupon Management | Database / Business Service | Customer, Staff | Records coupon usage atomically and enforces global/per-user usage limits during concurrent order creation. | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Week 1 | Not Started | II.11.5 | II.11.5 | Concurrent final-usage tests allow only permitted usage; failed order creates no orphan usage record. | EV-COUPON-05 / TC-COUPON-05 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
6 | PAY-01 | Payment Method Selection UI | Payment & Invoice | Customer / Staff UI | Customer, Staff | Allows selection of supported payment methods such as cash or QR and displays payable amount from the server. | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Week 1 | Doing | II.12.1 | II.12.1 | Selected method is submitted to the payment API; displayed amount matches server; unsupported method is blocked. | EV-PAY-01 / TC-PAY-01 | Payment selection/integration remains mixed; verify real PayOS/QR callback and persisted payment state.
7 | PAY-02 | Payment Processing API | Payment & Invoice | Backend API | Customer, Staff | Processes an eligible order payment request and returns an authoritative payment result. | Phạm Văn Quyết (DE190425) | Critical | Complex | 240 | Week 1 | Done | II.12.2 | II.12.2 | Successful request creates payment; invalid order/state/role fails; API is covered for cash/QR outcomes. | EV-PAY-02 / TC-PAY-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
8 | PAY-03 | Payment Amount Verification & Idempotency | Payment & Invoice | Business Service | Customer, Staff | Verifies payment amount against the final order total and prevents duplicate processing of the same request/order. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 1 | Done | II.12.3 | II.12.3 | Amount mismatch fails; repeated request returns the original result or safe conflict; no duplicate records are created. | EV-PAY-03 / TC-PAY-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
9 | PAY-04 | Persist Payment & Complete Order Transactionally | Payment & Invoice | Backend Service / DB | Customer, Staff | Stores payment details and updates the order to completed only within one successful transaction. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 1 | Done | II.12.4 | II.12.4 | Success creates one payment and completes order; failure rolls back; SQL evidence reconciles amount/status. | EV-PAY-04 / TC-PAY-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
10 | INV-01 | Invoice Entity & Unique Order Rule | Payment & Invoice | Database Migration | Customer, Staff, Admin | Creates immutable invoice persistence linked one-to-one with a successfully paid order. | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Week 2 | Not Started | II.13.1 | II.13.1 | Migration creates constraints; duplicate invoice creation fails; invoice values remain unchanged after menu updates. | EV-INV-01 / TC-INV-01 | Invoice persistence/generation/download is planned and depends on a verified successful payment flow.
11 | INV-02 | Generate Immutable Invoice after Payment | Payment & Invoice | Backend Service | Customer, Staff | Generates the invoice automatically within/after the successful payment transaction using order and payment snapshots. | Trần Thanh Gia Huy (DE180571) | Critical | Complex | 240 | Week 2 | Not Started | II.13.2 | II.13.2 | Each successful payment produces exactly one invoice; failed/duplicate payment produces none/one as appropriate. | EV-INV-02 / TC-INV-02 | Invoice persistence/generation/download is planned and depends on a verified successful payment flow.
12 | INV-03 | View / Download Invoice | Payment & Invoice | UI / Backend API | Customer, Staff, Admin | Allows authorized users to view invoice details and download/print a stable invoice representation. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 2 | Not Started | II.13.3 | II.13.3 | Authorized view/download works; unauthorized access fails; displayed/PDF totals match database. | EV-INV-03 / TC-INV-03 | Invoice persistence/generation/download is planned and depends on a verified successful payment flow.
13 | FB-01 | Submit Feedback Screen | Feedback Management | Customer UI | Customer | Collects rating and comment for an eligible completed order and displays validation/API responses. | Nguyễn Đức Thương (DE190096) | High | Medium | 120 | Week 2 | Doing | II.14.1 | II.14.1 | Eligible customer can submit once; invalid rating/comment is blocked; refresh shows persisted result after backend completion. | EV-FB-01 / TC-FB-01 | Frontend/backend integration or moderation evidence is incomplete; close with persistence and authorization proof.
14 | FB-02 | Feedback Persistence & Completed-order Eligibility | Feedback Management | Backend API / DB | Customer | Persists feedback only when the authenticated customer owns a completed eligible order. | Nguyễn Tiến Lộc (DE190986) | Critical | Complex | 240 | Week 2 | Done | II.14.2 | II.14.2 | Eligible feedback remains after refresh; ineligible/unauthorized requests fail; database relation is correct. | EV-FB-02 / TC-FB-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
15 | FB-03 | One Feedback per Order & Input Validation | Feedback Management | Business Service / DB | Customer | Enforces one active feedback record per customer order and validates rating/comment. | Nguyễn Tiến Lộc (DE190986) | High | Complex | 240 | Week 2 | Done | II.14.3 | II.14.3 | Duplicate/concurrent submissions create at most one record; invalid input returns field errors. | EV-FB-03 / TC-FB-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
16 | FB-04 | Admin Feedback Search / Moderation | Feedback Management | Admin Screen / API | Admin | Lists feedback with filters and permits controlled moderation status without rewriting the original rating history. | Trần Thanh Gia Huy (DE180571) | High | Complex | 240 | Week 2 | Doing | II.14.4 | II.14.4 | Admin can search/filter/review/moderate; non-admin is denied; moderation persists after refresh. | EV-FB-04 / TC-FB-04 | Frontend/backend integration or moderation evidence is incomplete; close with persistence and authorization proof.
17 | RPT-01 | Dashboard KPI Aggregation API | Reporting & Analytics | Backend Report API | Admin | Calculates operational KPIs such as paid revenue, completed orders, active reservations, and customer counts from live data. | Phan Nguyễn (DE191019) | Critical | Complex | 240 | Week 1 | Done | II.15.1 | II.15.1 | API values reconcile with direct SQL for the same period; empty period returns zero/no-data safely. | EV-RPT-01 / TC-RPT-01 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
18 | RPT-02 | Revenue Trend & Date Filter | Reporting & Analytics | Backend API / Admin UI | Admin | Groups paid revenue by day/month and supports date-range filtering for dashboard charts. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 1 | Done | II.15.2 | II.15.2 | Chart data matches SQL aggregation; changing date range refreshes correctly; empty ranges render safely. | EV-RPT-02 / TC-RPT-02 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
19 | RPT-03 | Top Food & Order-status Reports | Reporting & Analytics | Backend API / Admin UI | Admin | Reports top-selling foods and order counts by status using persisted order items and orders. | Phan Nguyễn (DE191019) | High | Complex | 240 | Week 2 | Done | II.15.3 | II.15.3 | Rankings/counts reconcile with SQL; filters and tie handling are documented; non-admin access is blocked. | EV-RPT-03 / TC-RPT-03 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
20 | RPT-04 | Dashboard Frontend Live-data Integration | Reporting & Analytics | Admin UI | Admin | Replaces hardcoded dashboard values with secured report API calls, loading states, errors, and no-data states. | Nguyễn Đức Thương (DE190096) | Critical | Complex | 240 | Week 2 | Done | II.15.4 | II.15.4 | Network evidence shows real API calls; displayed totals match response/SQL; API failure does not crash page. | EV-RPT-04 / TC-RPT-04 | Implemented in the audited ProjectSWP baseline; reconfirm build, test, UI/API, and database evidence against the final release tag.
21 | AI-01 | AI Analytics with Controlled Data & Logging | AI Support | Admin AI Function | Admin | Provides AI-assisted interpretation of selected report data with controlled inputs, advisory output, and audit logging. | Trần Thanh Gia Huy (DE180571) | Medium | Complex | 240 | Week 2 | Doing | II.16.1 | II.16.1 | Authorized admin receives a logged result; failures have safe fallback; output clearly states limitations. | EV-AI-01 / TC-AI-01 | Experimental/prototype capability only; advisory scope, safe fallback, logging, and live-server evidence must be demonstrated.
22 | AI-02 | Customer Chatbot FAQ & Safe Fallback | AI Support | Customer AI Function | Guest, Customer | Answers common restaurant/menu/reservation/order questions and routes unsupported requests to a safe fallback. | Trần Thanh Gia Huy (DE180571) | Medium | Complex | 240 | Week 2 | Doing | II.16.2 | II.16.2 | FAQ answers are relevant; unsafe/unknown prompts receive fallback; session-aware links do not leak data. | EV-AI-02 / TC-AI-02 | Experimental/prototype capability only; advisory scope, safe fallback, logging, and live-server evidence must be demonstrated.

## Dashboard
PROJECTSWP – FINAL DEFENSE READINESS DASHBOARD
Live summary from the Project sheet. Only Done/Updated items count as complete; experimental items remain open until production-grade verification.
Total Functions | Completed (Done + Updated) | Doing | Not Started | Completion % | Evidence Verified % | Critical Open Gaps | Target LOC Band
90 | 67 | 13 | 10 | 74.44% | 74.44% | 8 | 18420
Status | Functions |  | Iteration | Total | Complete | Open
Done | 50 |  | Iter1 | 25 | 25 | 0
Updated | 17 |  | Iter2 | 20 | 19 | 1
Doing | 13 |  | Iter3 | 23 | 14 | 9
Not Started | 10 |  | Iter4 | 22 | 9 | 13
Member | Total | Complete | Open | Target LOC | Completion %
Phan Nguyễn (DE191019) | 18 | 16 | 2 | 3600 | 88.89%
Phạm Văn Quyết (DE190425) | 18 | 18 | 0 | 3600 | 100%
Nguyễn Tiến Lộc (DE190986) | 18 | 13 | 5 | 3780 | 72.22%
Nguyễn Đức Thương (DE190096) | 18 | 13 | 5 | 3360 | 72.22%
Trần Thanh Gia Huy (DE180571) | 18 | 7 | 11 | 4080 | 38.89%
Critical Open Work ID | Function | Owner | Status | Iteration | Blocking Note
CART-04 | Cart Subtotal Calculation | Nguyễn Tiến Lộc (DE190986) | Doing | Iter3 | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
COUPON-01 | Coupon Entity & Database Migration | Trần Thanh Gia Huy (DE180571) | Not Started | Iter4 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
COUPON-02 | Admin Coupon List / Create / Update | Nguyễn Đức Thương (DE190096) | Not Started | Iter4 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
COUPON-03 | Coupon Eligibility Validation API | Trần Thanh Gia Huy (DE180571) | Not Started | Iter4 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
COUPON-04 | Apply Coupon Server-side to Order | Nguyễn Tiến Lộc (DE190986) | Not Started | Iter4 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
COUPON-05 | Coupon Usage Limit & Atomic Persistence | Trần Thanh Gia Huy (DE180571) | Not Started | Iter4 | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
INV-01 | Invoice Entity & Unique Order Rule | Trần Thanh Gia Huy (DE180571) | Not Started | Iter4 | Invoice persistence/generation/download is planned and depends on a verified successful payment flow.
INV-02 | Generate Immutable Invoice after Payment | Trần Thanh Gia Huy (DE180571) | Not Started | Iter4 | Invoice persistence/generation/download is planned and depends on a verified successful payment flow.

## Member Workload
MEMBER WORKLOAD & FINAL EVALUATION COVERAGE
Each member owns exactly 18 functional units. Target LOC bands are planning/evaluation bands (Simple 60, Medium 120, Complex 240), not a substitute for Git LOC evidence.
Member | Project Role | Total Items | Done/Updated | Doing | Not Started | Completion % | Target LOC | Critical Open | Evidence Missing | Iter1 | Iter2 | Iter3 | Iter4
Phan Nguyễn (DE191019) | Leader / Admin, Menu & Reporting | 18 | 16 | 1 | 1 | 88.89% | 3600 | 0 | 1 | 10 | 2 | 2 | 4
Phạm Văn Quyết (DE190425) | Backend & Security Lead | 18 | 18 | 0 | 0 | 100% | 3600 | 0 | 0 | 9 | 6 | 2 | 1
Nguyễn Tiến Lộc (DE190986) | Order, Kitchen & Transaction Flow | 18 | 13 | 4 | 1 | 72.22% | 3780 | 2 | 1 | 0 | 0 | 13 | 5
Nguyễn Đức Thương (DE190096) | Frontend Lead / Customer UX | 18 | 13 | 4 | 1 | 72.22% | 3360 | 1 | 1 | 6 | 4 | 4 | 4
Trần Thanh Gia Huy (DE180571) | Integration, Coupon, AI & Quality Support | 18 | 7 | 4 | 7 | 38.89% | 4080 | 5 | 7 | 0 | 8 | 2 | 8
Workload Interpretation
Rule 1 | Every member has 18 owned functional units across the semester, preventing a sparse or one-sided contribution record.
Rule 2 | Target LOC is a planning band. Final scoring evidence must come from Git contribution, code quality, and verified completed functions.
Rule 3 | Backend/security/transaction work naturally carries more Complex items; frontend work must still include API integration, validation, error handling, and test evidence.
Rule 4 | A member's row is not Final-ready while Critical Open or Evidence Missing is greater than zero.

## Gap Analysis
DETAILED CODE-AUDIT GAP ANALYSIS & FINAL CLOSURE PLAN
Every Doing/Not Started function is listed as a concrete closure item. Close a gap only after acceptance criteria and evidence are verified.
Gap ID | Work ID | Workstream | Code-audit Finding | Required Closure Action | Owner | Priority | Status | Acceptance Criteria | Evidence Required | Blocking Impact | Target | Evidence State
GAP-01 | SYS-02 | System Foundation | Manual SQL/schema setup remains; no verified Flyway migration baseline. | Complete and verify: Provides ordered migration scripts and safe reference seed data for table and reservation modules. | Trần Thanh Gia Huy (DE180571) | High | Doing | Flyway/migration history is successful; schema constraints/indexes exist; application starts with the clean database. | SYS-02: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-02 | CART-01 | Cart & Order Management | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Complete and verify: Adds an available menu item with selected quantity and notes to the customer's cart. | Nguyễn Tiến Lộc (DE190986) | High | Doing | Valid item appears once with correct quantity; unavailable/invalid item is blocked; feedback is immediate. | CART-01: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-03 | CART-02 | Cart & Order Management | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Complete and verify: Changes cart item quantity and rechecks current food availability and price constraints. | Nguyễn Tiến Lộc (DE190986) | High | Doing | Valid quantity updates subtotal; invalid quantity is rejected; unavailable items cannot proceed unnoticed. | CART-02: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-04 | CART-03 | Cart & Order Management | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Complete and verify: Removes one item or clears all cart items with confirmation where appropriate. | Nguyễn Tiến Lộc (DE190986) | Medium | Doing | Selected item is removed; clear empties the cart; repeated actions do not cause errors. | CART-03: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-05 | CART-04 | Cart & Order Management | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Complete and verify: Calculates subtotal from current authoritative food price and quantity before discounts and payment. | Nguyễn Tiến Lộc (DE190986) | Critical | Doing | Subtotal matches server calculation for multiple items/quantities; decimal rounding follows policy. | CART-04: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Blocks final release claim. | Before Final Submission | Partial
GAP-06 | CART-05 | Cart & Order Management | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified. | Complete and verify: Preserves the cart across page navigation and expected session lifecycle while keeping it scoped to the current user. | Nguyễn Đức Thương (DE190096) | Medium | Doing | Cart survives expected navigation/refresh; logout/user switch does not leak items; stale data is handled. | CART-05: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-07 | STAFF-01 | Staff Operations | Employee/table-assignment persistence and conflict rules are not verified in the current repository. | Complete and verify: Creates time-bounded staff-to-table assignments used by the service workspace. | Trần Thanh Gia Huy (DE180571) | High | Not Started | Valid assignment appears in workspace; invalid/inactive references are rejected; history is retained. | STAFF-01: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Missing
GAP-08 | STAFF-02 | Staff Operations | Employee/table-assignment persistence and conflict rules are not verified in the current repository. | Complete and verify: Prevents overlapping active assignments that violate the configured one-table/one-staff service policy. | Trần Thanh Gia Huy (DE180571) | High | Not Started | Conflicting assignment is rejected; non-overlapping assignment succeeds; concurrent tests preserve consistency. | STAFF-02: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Missing
GAP-09 | STAFF-03 | Staff Operations | Staff-facing behavior exists only partially; complete API integration, authorization, and evidence. | Complete and verify: Shows the logged-in staff member's assigned tables, current reservations, and active orders. | Nguyễn Đức Thương (DE190096) | High | Doing | Staff sees only assigned work; updates reflect order/table status changes; empty state is usable. | STAFF-03: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-10 | STAFF-04 | Staff Operations | Staff-facing behavior exists only partially; complete API integration, authorization, and evidence. | Complete and verify: Cancels an eligible order with a required reason and records who performed the action. | Phan Nguyễn (DE191019) | High | Doing | Allowed cancellation records reason/actor/time; forbidden state is rejected; order remains visible in history. | STAFF-04: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-11 | COUPON-01 | Coupon Management | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Complete and verify: Creates coupon and usage persistence with code, type, value, limits, validity period, status, and audit fields. | Trần Thanh Gia Huy (DE180571) | Critical | Not Started | Migration succeeds on a clean database; constraints reject invalid/duplicate records; entity mapping passes tests. | COUPON-01: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Blocks final release claim. | Before Final Submission | Missing
GAP-12 | COUPON-02 | Coupon Management | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Complete and verify: Provides secure coupon search, creation, editing, activation, and deactivation. | Nguyễn Đức Thương (DE190096) | Critical | Not Started | Admin CRUD persists correctly; invalid/duplicate data is rejected; non-admin mutation returns 403. | COUPON-02: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Blocks final release claim. | Before Final Submission | Missing
GAP-13 | COUPON-03 | Coupon Management | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Complete and verify: Validates coupon status, date, minimum amount, usage limits, role/customer eligibility, and applicable order context. | Trần Thanh Gia Huy (DE180571) | Critical | Not Started | Valid coupon returns authoritative discount preview; expired/inactive/over-limit/ineligible coupons are rejected. | COUPON-03: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Blocks final release claim. | Before Final Submission | Missing
GAP-14 | COUPON-04 | Coupon Management | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Complete and verify: Applies the validated coupon inside the order transaction and persists discount and final total. | Nguyễn Tiến Lộc (DE190986) | Critical | Not Started | Persisted order total matches server calculation; manipulated requests fail; transaction rolls back on invalid coupon. | COUPON-04: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Blocks final release claim. | Before Final Submission | Missing
GAP-15 | COUPON-05 | Coupon Management | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed. | Complete and verify: Records coupon usage atomically and enforces global/per-user usage limits during concurrent order creation. | Trần Thanh Gia Huy (DE180571) | Critical | Not Started | Concurrent final-usage tests allow only permitted usage; failed order creates no orphan usage record. | COUPON-05: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Blocks final release claim. | Before Final Submission | Missing
GAP-16 | PAY-01 | Payment & Invoice | Payment selection/integration remains mixed; verify real PayOS/QR callback and persisted payment state. | Complete and verify: Allows selection of supported payment methods such as cash or QR and displays payable amount from the server. | Nguyễn Đức Thương (DE190096) | High | Doing | Selected method is submitted to the payment API; displayed amount matches server; unsupported method is blocked. | PAY-01: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-17 | INV-01 | Payment & Invoice | Invoice persistence/generation/download is planned and depends on a verified successful payment flow. | Complete and verify: Creates immutable invoice persistence linked one-to-one with a successfully paid order. | Trần Thanh Gia Huy (DE180571) | Critical | Not Started | Migration creates constraints; duplicate invoice creation fails; invoice values remain unchanged after menu updates. | INV-01: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Blocks final release claim. | Before Final Submission | Missing
GAP-18 | INV-02 | Payment & Invoice | Invoice persistence/generation/download is planned and depends on a verified successful payment flow. | Complete and verify: Generates the invoice automatically within/after the successful payment transaction using order and payment snapshots. | Trần Thanh Gia Huy (DE180571) | Critical | Not Started | Each successful payment produces exactly one invoice; failed/duplicate payment produces none/one as appropriate. | INV-02: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Blocks final release claim. | Before Final Submission | Missing
GAP-19 | INV-03 | Payment & Invoice | Invoice persistence/generation/download is planned and depends on a verified successful payment flow. | Complete and verify: Allows authorized users to view invoice details and download/print a stable invoice representation. | Phan Nguyễn (DE191019) | High | Not Started | Authorized view/download works; unauthorized access fails; displayed/PDF totals match database. | INV-03: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Missing
GAP-20 | FB-01 | Feedback Management | Frontend/backend integration or moderation evidence is incomplete; close with persistence and authorization proof. | Complete and verify: Collects rating and comment for an eligible completed order and displays validation/API responses. | Nguyễn Đức Thương (DE190096) | High | Doing | Eligible customer can submit once; invalid rating/comment is blocked; refresh shows persisted result after backend completion. | FB-01: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-21 | FB-04 | Feedback Management | Frontend/backend integration or moderation evidence is incomplete; close with persistence and authorization proof. | Complete and verify: Lists feedback with filters and permits controlled moderation status without rewriting the original rating history. | Trần Thanh Gia Huy (DE180571) | High | Doing | Admin can search/filter/review/moderate; non-admin is denied; moderation persists after refresh. | FB-04: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Partial
GAP-22 | AI-01 | AI Support | Experimental/prototype capability only; advisory scope, safe fallback, logging, and live-server evidence must be demonstrated. | Complete and verify: Provides AI-assisted interpretation of selected report data with controlled inputs, advisory output, and audit logging. | Trần Thanh Gia Huy (DE180571) | Medium | Doing | Authorized admin receives a logged result; failures have safe fallback; output clearly states limitations. | AI-01: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Experimental
GAP-23 | AI-02 | AI Support | Experimental/prototype capability only; advisory scope, safe fallback, logging, and live-server evidence must be demonstrated. | Complete and verify: Answers common restaurant/menu/reservation/order questions and routes unsupported requests to a safe fallback. | Trần Thanh Gia Huy (DE180571) | Medium | Doing | FAQ answers are relevant; unsafe/unknown prompts receive fallback; session-aware links do not leak data. | AI-02: final-tag commit; automated/API test; UI/network screenshot where applicable; database proof; RDS/SDS reconciliation. | Must be disclosed or closed before defense. | Before Final Submission | Experimental

## Traceability
PROJECTSWP – REQUIREMENT / DESIGN / CODE / TEST TRACEABILITY
Expected technical objects must be verified against the final tagged repository. This matrix prevents SRS/SDS/project tracking from drifting away from code.
Work ID | SRS Ref | SDS Ref | Expected UI / Route | Expected API / Service | Expected DB Object | Test Case ID | Evidence ID | Evidence Status | Verification Notes
AUTH-01 | II.1.1 | II.1.1 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-01 | EV-AUTH-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-02 | II.1.2 | II.1.2 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-02 | EV-AUTH-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-03 | II.1.3 | II.1.3 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-03 | EV-AUTH-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-04 | II.1.4 | II.1.4 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-04 | EV-AUTH-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-05 | II.1.5 | II.1.5 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-05 | EV-AUTH-05 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-06 | II.1.6 | II.1.6 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-06 | EV-AUTH-06 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-07 | II.1.7 | II.1.7 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-07 | EV-AUTH-07 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-08 | II.1.8 | II.1.8 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-08 | EV-AUTH-08 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-09 | II.1.9 | II.1.9 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-09 | EV-AUTH-09 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-10 | II.1.10 | II.1.10 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-10 | EV-AUTH-10 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-11 | II.1.11 | II.1.11 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-11 | EV-AUTH-11 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-12 | II.1.12 | II.1.12 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-12 | EV-AUTH-12 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-13 | II.1.13 | II.1.13 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-13 | EV-AUTH-13 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AUTH-14 | II.1.14 | II.1.14 | /login, /register, /forgot-password | /api/auth/*; security filter | users, roles, refresh_tokens | TC-AUTH-14 | EV-AUTH-14 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
USER-01 | II.2.1 | II.2.1 | /profile, /admin/accounts | /api/users/*; /api/users/me | users, roles | TC-USER-01 | EV-USER-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
USER-02 | II.2.2 | II.2.2 | /profile, /admin/accounts | /api/users/*; /api/users/me | users, roles | TC-USER-02 | EV-USER-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
USER-03 | II.2.3 | II.2.3 | /profile, /admin/accounts | /api/users/*; /api/users/me | users, roles | TC-USER-03 | EV-USER-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
USER-04 | II.2.4 | II.2.4 | /profile, /admin/accounts | /api/users/*; /api/users/me | users, roles | TC-USER-04 | EV-USER-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
MENU-01 | II.3.1 | II.3.1 | /menu, /admin/categories, /admin/foods | /api/categories; /api/foods | categories, foods | TC-MENU-01 | EV-MENU-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
MENU-02 | II.3.2 | II.3.2 | /menu, /admin/categories, /admin/foods | /api/categories; /api/foods | categories, foods | TC-MENU-02 | EV-MENU-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
MENU-03 | II.3.3 | II.3.3 | /menu, /admin/categories, /admin/foods | /api/categories; /api/foods | categories, foods | TC-MENU-03 | EV-MENU-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
MENU-04 | II.3.4 | II.3.4 | /menu, /admin/categories, /admin/foods | /api/categories; /api/foods | categories, foods | TC-MENU-04 | EV-MENU-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
MENU-05 | II.3.5 | II.3.5 | /menu, /admin/categories, /admin/foods | /api/categories; /api/foods | categories, foods | TC-MENU-05 | EV-MENU-05 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
MENU-06 | II.3.6 | II.3.6 | /menu, /admin/categories, /admin/foods | /api/categories; /api/foods | categories, foods | TC-MENU-06 | EV-MENU-06 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
MENU-07 | II.3.7 | II.3.7 | /menu, /admin/categories, /admin/foods | /api/categories; /api/foods | categories, foods | TC-MENU-07 | EV-MENU-07 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
TABLE-01 | II.4.1 | II.4.1 | /tables, /admin/tables | /api/tables | restaurant_tables | TC-TABLE-01 | EV-TABLE-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
TABLE-02 | II.4.2 | II.4.2 | /tables, /admin/tables | /api/tables | restaurant_tables | TC-TABLE-02 | EV-TABLE-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
TABLE-03 | II.4.3 | II.4.3 | /tables, /admin/tables | /api/tables | restaurant_tables | TC-TABLE-03 | EV-TABLE-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
TABLE-04 | II.4.4 | II.4.4 | /tables, /admin/tables | /api/tables | restaurant_tables | TC-TABLE-04 | EV-TABLE-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
TABLE-05 | II.4.5 | II.4.5 | /tables, /admin/tables | /api/tables | restaurant_tables | TC-TABLE-05 | EV-TABLE-05 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
TABLE-06 | II.4.6 | II.4.6 | /tables, /admin/tables | /api/tables | restaurant_tables | TC-TABLE-06 | EV-TABLE-06 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-01 | II.5.1 | II.5.1 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-01 | EV-RES-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-02 | II.5.2 | II.5.2 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-02 | EV-RES-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-03 | II.5.3 | II.5.3 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-03 | EV-RES-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-04 | II.5.4 | II.5.4 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-04 | EV-RES-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-05 | II.5.5 | II.5.5 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-05 | EV-RES-05 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-06 | II.5.6 | II.5.6 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-06 | EV-RES-06 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-07 | II.5.7 | II.5.7 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-07 | EV-RES-07 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-08 | II.5.8 | II.5.8 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-08 | EV-RES-08 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-09 | II.5.9 | II.5.9 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-09 | EV-RES-09 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-10 | II.5.10 | II.5.10 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-10 | EV-RES-10 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-11 | II.5.11 | II.5.11 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-11 | EV-RES-11 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RES-12 | II.5.12 | II.5.12 | /reservations, /admin/reservations | /api/reservations | reservations, restaurant_tables | TC-RES-12 | EV-RES-12 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
SYS-01 | II.6.1 | II.6.1 | N/A | Global exception handling / migration | flyway_schema_history; shared schema | TC-SYS-01 | EV-SYS-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
SYS-02 | II.6.2 | II.6.2 | N/A | Global exception handling / migration | flyway_schema_history; shared schema | TC-SYS-02 | EV-SYS-02 | Partial | Manual SQL/schema setup remains; no verified Flyway migration baseline.
CART-01 | II.7.1 | II.7.1 | /cart | Cart store and/or /api/cart | carts, cart_items (if persisted) | TC-CART-01 | EV-CART-01 | Partial | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
CART-02 | II.7.2 | II.7.2 | /cart | Cart store and/or /api/cart | carts, cart_items (if persisted) | TC-CART-02 | EV-CART-02 | Partial | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
CART-03 | II.7.3 | II.7.3 | /cart | Cart store and/or /api/cart | carts, cart_items (if persisted) | TC-CART-03 | EV-CART-03 | Partial | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
CART-04 | II.7.4 | II.7.4 | /cart | Cart store and/or /api/cart | carts, cart_items (if persisted) | TC-CART-04 | EV-CART-04 | Partial | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
CART-05 | II.7.5 | II.7.5 | /cart | Cart store and/or /api/cart | carts, cart_items (if persisted) | TC-CART-05 | EV-CART-05 | Partial | Frontend cart flow exists, but persistence is browser/local-state based and no durable backend cart was verified.
ORDER-01 | II.8.1 | II.8.1 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-01 | EV-ORDER-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-02 | II.8.2 | II.8.2 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-02 | EV-ORDER-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-03 | II.8.3 | II.8.3 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-03 | EV-ORDER-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-04 | II.8.4 | II.8.4 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-04 | EV-ORDER-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-05 | II.8.5 | II.8.5 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-05 | EV-ORDER-05 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-06 | II.8.6 | II.8.6 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-06 | EV-ORDER-06 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-07 | II.8.7 | II.8.7 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-07 | EV-ORDER-07 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-08 | II.8.8 | II.8.8 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-08 | EV-ORDER-08 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-09 | II.8.9 | II.8.9 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-09 | EV-ORDER-09 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
ORDER-10 | II.8.10 | II.8.10 | /orders, /staff/orders | /api/orders | restaurant_orders, order_items | TC-ORDER-10 | EV-ORDER-10 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
STAFF-01 | II.9.1 | II.9.1 | /staff/workspace | /api/table-assignments | employees, table_assignments, restaurant_tables | TC-STAFF-01 | EV-STAFF-01 | Missing | Employee/table-assignment persistence and conflict rules are not verified in the current repository.
STAFF-02 | II.9.2 | II.9.2 | /staff/workspace | /api/table-assignments | employees, table_assignments, restaurant_tables | TC-STAFF-02 | EV-STAFF-02 | Missing | Employee/table-assignment persistence and conflict rules are not verified in the current repository.
STAFF-03 | II.9.3 | II.9.3 | /staff/workspace | /api/table-assignments | employees, table_assignments, restaurant_tables | TC-STAFF-03 | EV-STAFF-03 | Partial | Staff-facing behavior exists only partially; complete API integration, authorization, and evidence.
STAFF-04 | II.9.4 | II.9.4 | /staff/workspace | /api/table-assignments | employees, table_assignments, restaurant_tables | TC-STAFF-04 | EV-STAFF-04 | Partial | Staff-facing behavior exists only partially; complete API integration, authorization, and evidence.
KITCHEN-01 | II.10.1 | II.10.1 | /kitchen | /api/kitchen/orders | restaurant_orders, order_items | TC-KITCHEN-01 | EV-KITCHEN-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
KITCHEN-02 | II.10.2 | II.10.2 | /kitchen | /api/kitchen/orders | restaurant_orders, order_items | TC-KITCHEN-02 | EV-KITCHEN-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
KITCHEN-03 | II.10.3 | II.10.3 | /kitchen | /api/kitchen/orders | restaurant_orders, order_items | TC-KITCHEN-03 | EV-KITCHEN-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
KITCHEN-04 | II.10.4 | II.10.4 | /kitchen | /api/kitchen/orders | restaurant_orders, order_items | TC-KITCHEN-04 | EV-KITCHEN-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
COUPON-01 | II.11.1 | II.11.1 | /admin/coupons, /checkout | /api/coupons | coupons, coupon_usages | TC-COUPON-01 | EV-COUPON-01 | Missing | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
COUPON-02 | II.11.2 | II.11.2 | /admin/coupons, /checkout | /api/coupons | coupons, coupon_usages | TC-COUPON-02 | EV-COUPON-02 | Missing | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
COUPON-03 | II.11.3 | II.11.3 | /admin/coupons, /checkout | /api/coupons | coupons, coupon_usages | TC-COUPON-03 | EV-COUPON-03 | Missing | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
COUPON-04 | II.11.4 | II.11.4 | /admin/coupons, /checkout | /api/coupons | coupons, coupon_usages | TC-COUPON-04 | EV-COUPON-04 | Missing | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
COUPON-05 | II.11.5 | II.11.5 | /admin/coupons, /checkout | /api/coupons | coupons, coupon_usages | TC-COUPON-05 | EV-COUPON-05 | Missing | Coupon lifecycle and server-side eligibility/usage enforcement are planned; do not present as completed.
PAY-01 | II.12.1 | II.12.1 | /payment | /api/payments | payments, restaurant_orders | TC-PAY-01 | EV-PAY-01 | Partial | Payment selection/integration remains mixed; verify real PayOS/QR callback and persisted payment state.
PAY-02 | II.12.2 | II.12.2 | /payment | /api/payments | payments, restaurant_orders | TC-PAY-02 | EV-PAY-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
PAY-03 | II.12.3 | II.12.3 | /payment | /api/payments | payments, restaurant_orders | TC-PAY-03 | EV-PAY-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
PAY-04 | II.12.4 | II.12.4 | /payment | /api/payments | payments, restaurant_orders | TC-PAY-04 | EV-PAY-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
INV-01 | II.13.1 | II.13.1 | /invoices | /api/invoices | invoices, payments, restaurant_orders | TC-INV-01 | EV-INV-01 | Missing | Invoice persistence/generation/download is planned and depends on a verified successful payment flow.
INV-02 | II.13.2 | II.13.2 | /invoices | /api/invoices | invoices, payments, restaurant_orders | TC-INV-02 | EV-INV-02 | Missing | Invoice persistence/generation/download is planned and depends on a verified successful payment flow.
INV-03 | II.13.3 | II.13.3 | /invoices | /api/invoices | invoices, payments, restaurant_orders | TC-INV-03 | EV-INV-03 | Missing | Invoice persistence/generation/download is planned and depends on a verified successful payment flow.
FB-01 | II.14.1 | II.14.1 | /feedback, /admin/feedback | /api/feedbacks | feedbacks, restaurant_orders | TC-FB-01 | EV-FB-01 | Partial | Frontend/backend integration or moderation evidence is incomplete; close with persistence and authorization proof.
FB-02 | II.14.2 | II.14.2 | /feedback, /admin/feedback | /api/feedbacks | feedbacks, restaurant_orders | TC-FB-02 | EV-FB-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
FB-03 | II.14.3 | II.14.3 | /feedback, /admin/feedback | /api/feedbacks | feedbacks, restaurant_orders | TC-FB-03 | EV-FB-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
FB-04 | II.14.4 | II.14.4 | /feedback, /admin/feedback | /api/feedbacks | feedbacks, restaurant_orders | TC-FB-04 | EV-FB-04 | Partial | Frontend/backend integration or moderation evidence is incomplete; close with persistence and authorization proof.
RPT-01 | II.15.1 | II.15.1 | /admin/dashboard, /admin/reports | /api/reports | payments, restaurant_orders, order_items, reservations | TC-RPT-01 | EV-RPT-01 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RPT-02 | II.15.2 | II.15.2 | /admin/dashboard, /admin/reports | /api/reports | payments, restaurant_orders, order_items, reservations | TC-RPT-02 | EV-RPT-02 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RPT-03 | II.15.3 | II.15.3 | /admin/dashboard, /admin/reports | /api/reports | payments, restaurant_orders, order_items, reservations | TC-RPT-03 | EV-RPT-03 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
RPT-04 | II.15.4 | II.15.4 | /admin/dashboard, /admin/reports | /api/reports | payments, restaurant_orders, order_items, reservations | TC-RPT-04 | EV-RPT-04 | Verified | Implemented in the current baseline; reconfirm all evidence against the final release tag.
AI-01 | II.16.1 | II.16.1 | /ai-analytics, /chatbot | /api/ai | AI audit/log storage if configured | TC-AI-01 | EV-AI-01 | Experimental | Experimental/prototype capability only; advisory scope, safe fallback, logging, and live-server evidence must be demonstrated.
AI-02 | II.16.2 | II.16.2 | /ai-analytics, /chatbot | /api/ai | AI audit/log storage if configured | TC-AI-02 | EV-AI-02 | Experimental | Experimental/prototype capability only; advisory scope, safe fallback, logging, and live-server evidence must be demonstrated.

## Guide & DoD
PROJECT TRACKING GUIDE, STATUS DEFINITIONS & CODE-AUDIT DoD
This sheet defines how the group must update the official final-evaluation tracker consistently.
Status | Meaning | Allowed Evidence State | Upgrade Condition | Complexity | Evaluation LOC Band | Interpretation
Not Started | No auditable implementation is available. | Missing | Create code/design/migration/test evidence before changing status. | Simple | 60 | Small isolated function with limited rules/dependencies.
Doing | Some implementation exists but acceptance criteria or evidence is incomplete. | Partial | Complete all acceptance criteria and required evidence. | Medium | 120 | Integrated UI/API function or moderate business validation.
Done | Implemented as planned and verified against the tagged code. | Verified | All Code-Audit DoD items pass. | Complex | 240 | Transaction, security, concurrency, financial, or multi-layer function.
Updated | Previously completed function was materially improved in a later iteration and reverified. | Verified | Original and updated behavior are documented and tested.
|  |  |  | DoD ID | Code-Audit Definition of Done | Required Evidence
Priority | Definition | Response | Examples | DoD-01 | Source code exists in the final tagged release and builds successfully. | Commit/PR/tag and build/CI result.
Critical | Release/security/financial integrity or core workflow blocker. | Must close before final tag. | JWT, role authorization, order total, coupon, payment, invoice. | DoD-02 | Required database migration runs on a clean database. | Migration file, Flyway history, SQL screenshot.
High | Important functional or data-integrity requirement. | Close before final demo unless explicitly excluded. | User CRUD, reservation concurrency, feedback persistence, reports. | DoD-03 | Backend API/business logic is validated and secured. | Controller/service/repository code and API tests.
Medium | Useful function with limited release risk. | Complete if in scope; otherwise document limitation. | Filters, history views, AI assistance. | DoD-04 | Frontend consumes the real API; no production mock/local-only data remains. | Network evidence and screenshots.
Low | Optional enhancement. | May be deferred with teacher approval. | Cosmetic or non-essential improvements. | DoD-05 | Happy path, validation, authorization, duplicate/concurrency, and error cases pass. | Unit/integration/Postman/test report.
|  |  |  | DoD-06 | SRS and SDS match behavior, database, classes, and sequence. | Updated document references.
|  |  |  | DoD-07 | Evidence is registered by Evidence ID and available for defense. | Evidence folder/link/index.
Update Workflow
1 | Member implements the function on the assigned branch and runs self-test.
2 | Member updates SRS/SDS and prepares test/evidence using the Work ID.
3 | Reviewer checks acceptance criteria and traceability against code/database.
4 | Only after review, update Evidence Status to Verified and Status to Done/Updated.
5 | Before iteration/final demo, reconcile Project, Iter sheet, Gap Analysis, and Traceability.

## Change Log
PROJECT TRACKING CHANGE LOG
Version | Date | Change Type | In Charge | Change Description | Approval / Note
1.0 | 2026-07-12 | Added | Group 01 | Initial high-level project tracking created from product feature groups. | Superseded because the scope was too coarse for final evaluation.
1.1 | 2026-07-12 | Modified | Group 01 | Statuses aligned with code-audit gaps for JWT, Admin Accounts, Coupon, Payment/Invoice, Feedback, and Reports. | Established audit-safe baseline.
2.0 | 2026-07-13 | Modified | Group 01 | Expanded to 90 auditable functions; added balanced ownership, acceptance criteria, LOC bands, dashboard, gap analysis, traceability, workload, and DoD. | Recommended final-evaluation working baseline.
3.0 | 2026-07-29 | Verified / Reconciled | Group 01 | Reconciled all 90 work items to the ProjectSWP code audit; synchronized iteration sheets, traceability, gaps, dashboard, Vietnamese member names, and added final submission gates. | Submission candidate; evidence must still be captured against the final release tag.

## Submission Readiness
PROJECTSWP – SUBMISSION READINESS & DEFENSE CHECKLIST
Use this page as the final gate. Green metrics are calculated from Project; checklist evidence must be attached to the exact final release tag.
Metric | Value | Gate | Current Assessment | Owner | Evidence / Action | Due | Decision
Total tracked functions | 90 | 90 | Scope coverage | Group 01 | Project sheet | Before submission | Controlled
Completed functions | 67 | Maximize; no false Done | Calculated | Group 01 | Dashboard + final tag | Before submission | Review
Completion rate | 74.44% | Disclose remaining scope | Calculated | Leader | Dashboard | Before submission | Review
Critical open gaps | 8 | 0 for release claim | Calculated | Technical leads | Gap Analysis | Before submission | Block if > 0
Evidence verified rate | 74.44% | 100% for claimed Done | Calculated | QA / Leader | Evidence register | Before defense | Review
Experimental items | 2 | Label explicitly | Calculated | AI owner | Demo limitations + logs | Before defense | Controlled
Gate ID | Submission Item | Required Proof | Responsible | Status | Risk if Missing | Final Check | Notes
G-01 | Final release tag | Immutable Git tag/commit hash matching submitted source | Leader | Pending | Cannot reproduce defended build | ☐ | Record hash in evidence folder.
G-02 | Backend verification | All automated tests pass; currently audited baseline reported 70/70 | Backend Lead | Re-run | Regression may remain hidden | ☐ | Attach test report from final tag.
G-03 | Frontend production build | Clean install and production build result | Frontend Lead | Pending | Demo may fail on another machine | ☐ | Attach build log and environment versions.
G-04 | Database setup | Clean SQL Server setup/migration and seed proof | Backend Lead | Pending | Project cannot be reproduced | ☐ | No verified Flyway baseline; document manual SQL precisely.
G-05 | API evidence | Postman/Swagger collection for main and negative flows | Backend Lead | Pending | Claims cannot be demonstrated | ☐ | Include 401/403, validation, duplicate, ownership cases.
G-06 | UI evidence | Screenshots/video and network calls for every claimed UI flow | Frontend Lead | Pending | UI may be mock/local-only | ☐ | Prioritize cart, payment, feedback, reports.
G-07 | RDS/SDS consistency | Work IDs and statuses match RDS_restaurant_1 and SDS_ProjectSWP | Leader | Review | Documentation contradiction | ☐ | Use Traceability sheet as index.
G-08 | Known limitations | Planned/partial/experimental scope disclosed honestly | Leader | Ready | Overclaim risk during defense | ☐ | Coupon, invoice, staff assignment, cart persistence, AI.
G-09 | Demo data | Repeatable accounts, roles, tables, menu, orders and payments | QA / Integration | Pending | Demo stalls or produces inconsistent results | ☐ | Prepare reset script and role credentials securely.
G-10 | Defense package | Workbook, RDS, SDS, source, test/evidence index and backup | All members | Pending | Incomplete submission package | ☐ | Open every file once on submission machine.